## Cover
GasGuard Suite — Integrated Budget Model
Prepared by Smart Innovations Ghana Limited (SIGL) for Ghana National Gas Company (GNGC)
CONFIDENTIAL — Prepared exclusively for GNGC evaluation purposes ¦ July 2026
How this workbook works
This workbook contains a single, project-wide budget of GHS 16,000,000 (tax-inclusive), phased in line with Section 6 of the SIGL proposal (Phase 0 - Phase 3). All figures are driven from the Assumptions tab: change any blue cell there and every phase tab, plus the Summary tab, recalculates automatically.
Tab | Purpose
Assumptions | Master control tab. Set the total contract value, the effective tax rate, the % of budget allocated to each phase, and the % split of each phase across cost categories (hardware, software, professional services, training, project management, contingency). Also sets the illustrative Year 2+ support fee.
Summary | Roll-up of all four phases: tax-exclusive subtotal, tax, and tax-inclusive total per phase, reconciled against the Assumptions tab.
Phase 0 - Diagnostic | Joint diagnostic assessment (Weeks 1-6): infrastructure review, data review, site survey, business case.
Phase 1 - Foundational | Foundational modules (Months 2-8): GasGuard Reconcile, GasGuard FieldLink, core GasGuard Fusion dashboard.
Phase 2 - Corridor-Fleet | Corridor and fleet instrumentation (Months 6-14): GasGuard FiberWatch, GasGuard TrackTrace, GasGuard SkyView.
Phase 3 - Marking-Fusion | Product marking and full fusion (Months 12-18): GasGuard MarkChain and full AI/ML fusion-layer integration.
Colour legend
Blue text | Editable input — safe to change.
Black text | Formula calculated within the same sheet — do not overtype.
Green text | Formula linked from another sheet (usually Assumptions) — do not overtype.
Note on tax | The effective rate combines VAT (15%), NHIL (2.5%) and GETFund (2.5%) on the same base, per Ghana's VAT Act, 2025 (Act 1151), effective 1 January 2026 (Ghana Revenue Authority). Adjust the rate in Assumptions!C8 if regulations change.

## Assumptions
GasGuard Suite — Master Budget Assumptions
Ghana National Gas Company (GNGC) — Integrated Pipeline Monitoring, Loss-Prevention & Custody-Integrity Platform
EDIT ONLY THE BLUE CELLS BELOW. All phase, category and summary totals recalculate automatically from these inputs.
1. CONTRACT VALUE & TAX
| Total Contract Value (Tax-Inclusive, GHS) | 16000000
| Effective Tax Rate (VAT 15% + NHIL 2.5% + GETFund 2.5%, same base) | 20%
| Tax-Exclusive Contract Value (GHS) | 13333333.3333
| Total Tax Amount (GHS) | 2666666.6667
Source: Ghana Revenue Authority, VAT Act, 2025 (Act 1151), effective 1 January 2026 (combined VAT + NHIL + GETFund = 20.0% effective rate). https://gra.gov.gh/domestic-tax/tax-types/vat/
2. PHASE ALLOCATION (% of Tax-Exclusive Contract Value)
| Phase | % Allocation | Tax-Exclusive Amount (GHS) | Tax (GHS) | Tax-Inclusive Amount (GHS)
| Phase 0 - Diagnostic Assessment | 3% | 400000 | 80000 | 480000
| Phase 1 - Foundational Modules | 32% | 4266666.6667 | 853333.3333 | 5120000
| Phase 2 - Corridor & Fleet Instrumentation | 40% | 5333333.3333 | 1066666.6667 | 6400000
| Phase 3 - Product Marking & Full Fusion | 25% | 3333333.3333 | 666666.6667 | 4000000
| TOTAL | 100% | 13333333.3333 | 2666666.6667 | 16000000
| Check: % Allocation sums to 100%? | OK
3. COST CATEGORY ALLOCATION (% within each Phase — each column must total 100%)
| Cost Category | Phase 0 | Phase 1 | Phase 2 | Phase 3
| Hardware & Equipment Procurement | 0% | 25% | 45% | 15%
| Software Licensing & Platform Integration | 0% | 35% | 25% | 35%
| Professional Services & Implementation | 55% | 25% | 20% | 30%
| Training & Knowledge Transfer | 10% | 5% | 4% | 8%
| Project Management & Governance | 20% | 5% | 4% | 7%
| Contingency | 15% | 5% | 2% | 5%
| TOTAL (must equal 100%) | 100% | 100% | 100% | 100%
4. YEAR 2+ ANNUAL SUPPORT & SUBSCRIPTION (illustrative — NOT included in the GHS 16,000,000 Phase 0-3 total)
| Annual Support Fee (% of cumulative Software Licensing value) | 18%
| Cumulative Software Licensing Value (Tax-Exclusive, GHS) | 3993333.3333
| Annual Support Fee (Tax-Exclusive, GHS) | 718800
| Annual Support Fee (Tax-Inclusive, GHS) | 862560
Recommended commercial structure per proposal Section 8: one-time integration/implementation fees (Phases 0-3 above) plus an annual software-and-support subscription beginning in Year 2, following Phase 1 go-live.

## Summary
GasGuard Suite — Budget Summary
Roll-up of all phases, reconciled against the Assumptions tab. Change inputs on the Assumptions tab; this sheet updates automatically.
| Phase | Subtotal (Tax-Excl, GHS) | Tax (GHS) | Total (Tax-Incl, GHS) | % of Project
| Phase 0 - Diagnostic Assessment | 400000 | 80000 | 480000 | 3%
| Phase 1 - Foundational Modules | 4266666.6667 | 853333.3333 | 5120000 | 32%
| Phase 2 - Corridor & Fleet Instrumentation | 5333333.3333 | 1066666.6667 | 6400000 | 40%
| Phase 3 - Product Marking & Full Fusion | 3333333.3333 | 666666.6667 | 4000000 | 25%
| GRAND TOTAL | 13333333.3333 | 2666666.6667 | 16000000 | 100%
| Check: Grand Total = Assumptions Total Contract Value? |  |  | OK
COST CATEGORY ROLL-UP (across all phases, Tax-Exclusive GHS)
| Cost Category | Total (Tax-Excl, GHS)
| Hardware & Equipment Procurement | 3966666.6667
| Software Licensing & Platform Integration | 3993333.3333
| Professional Services & Implementation | 3353333.3333
| Training & Knowledge Transfer | 733333.3333
| Project Management & Governance | 740000
| Contingency | 546666.6667
| TOTAL | 13333333.3333

## Phase 0 - Diagnostic
PHASE 0 — Joint Diagnostic Assessment
Weeks 1-6 ¦ SCADA/metering/reporting review, internal loss-data review (NDA), site survey, GNGC-specific business case
| Phase Total (Tax-Exclusive, GHS) | 400000
| Effective Tax Rate | 20%
| Phase Total (Tax-Inclusive, GHS) | 480000
| Cost Category / Line Item | Weight | Amount (Tax-Excl, GHS)
| PROFESSIONAL SERVICES & IMPLEMENTATION | 55% | 220000
| Site survey & data review (Atuabo plant, offshore WAGP corridor, LPG routes) | 50% | 110000
| SCADA / metering infrastructure review | 30% | 66000
| Business case & prioritized deployment plan development | 20% | 44000
| PROJECT MANAGEMENT & GOVERNANCE | 20% | 80000
| Phase 0 project coordination & GNGC liaison | 100% | 80000
| TRAINING & KNOWLEDGE TRANSFER | 10% | 40000
| Kickoff workshops with GNGC technical, integrity & IT/OT teams | 100% | 40000
| CONTINGENCY | 15% | 60000
| Contingency reserve | 100% | 60000
| SUBTOTAL (Tax-Exclusive, GHS) |  | 400000
| Tax (Effective Rate) |  | 80000
| TOTAL (Tax-Inclusive, GHS) |  | 480000
| Check vs Assumptions Phase Total |  | OK

## Phase 1 - Foundational
PHASE 1 — Foundational Modules
Months 2-8 ¦ GasGuard Reconcile across custody-transfer points, GasGuard FieldLink at priority sites, core GasGuard Fusion dashboard
| Phase Total (Tax-Exclusive, GHS) | 4266666.6667
| Effective Tax Rate | 20%
| Phase Total (Tax-Inclusive, GHS) | 5120000
| Cost Category / Line Item | Weight | Amount (Tax-Excl, GHS)
| HARDWARE & EQUIPMENT PROCUREMENT | 25% | 1066666.6667
| IoT LPWAN / cellular sensors & gateways (GasGuard FieldLink) | 70% | 746666.6667
| Metering interface / integration hardware (GasGuard Reconcile) | 30% | 320000
| SOFTWARE LICENSING & PLATFORM INTEGRATION | 35% | 1493333.3333
| GasGuard Reconcile (CPM mass-balance) licensing & configuration | 45% | 672000
| GasGuard Fusion core dashboard build | 40% | 597333.3333
| SCADA / telemetry data-integration connectors | 15% | 224000
| PROFESSIONAL SERVICES & IMPLEMENTATION | 25% | 1066666.6667
| Field deployment & commissioning | 60% | 640000
| Systems integration & testing | 40% | 426666.6667
| TRAINING & KNOWLEDGE TRANSFER | 5% | 213333.3333
| Control-room & field-staff training | 100% | 213333.3333
| PROJECT MANAGEMENT & GOVERNANCE | 5% | 213333.3333
| Phase 1 project management | 100% | 213333.3333
| CONTINGENCY | 5% | 213333.3333
| Contingency reserve | 100% | 213333.3333
| SUBTOTAL (Tax-Exclusive, GHS) |  | 4266666.6667
| Tax (Effective Rate) |  | 853333.3333
| TOTAL (Tax-Inclusive, GHS) |  | 5120000
| Check vs Assumptions Phase Total |  | OK

## Phase 2 - Corridor-Fleet
PHASE 2 — Corridor & Fleet Instrumentation
Months 6-14 ¦ GasGuard FiberWatch on the offshore WAGP corridor, GasGuard TrackTrace on the LPG bulk-vehicle fleet, GasGuard SkyView onboarding
| Phase Total (Tax-Exclusive, GHS) | 5333333.3333
| Effective Tax Rate | 20%
| Phase Total (Tax-Inclusive, GHS) | 6400000
| Cost Category / Line Item | Weight | Amount (Tax-Excl, GHS)
| HARDWARE & EQUIPMENT PROCUREMENT | 45% | 2400000
| Fiber-optic DAS interrogator units & cabling (GasGuard FiberWatch) | 55% | 1320000
| Tamper-evident flow meters & GPS telematics units (GasGuard TrackTrace) | 30% | 720000
| Satellite imagery subscription setup (GasGuard SkyView) | 15% | 360000
| SOFTWARE LICENSING & PLATFORM INTEGRATION | 25% | 1333333.3333
| DAS analytics & AIS vessel-tracking fusion | 40% | 533333.3333
| TrackTrace fleet-management software | 35% | 466666.6667
| SkyView satellite data integration | 25% | 333333.3333
| PROFESSIONAL SERVICES & IMPLEMENTATION | 20% | 1066666.6667
| Offshore corridor installation & commissioning | 50% | 533333.3333
| LPG bulk-fleet instrumentation rollout | 50% | 533333.3333
| TRAINING & KNOWLEDGE TRANSFER | 4% | 213333.3333
| Enforcement & field-team training | 100% | 213333.3333
| PROJECT MANAGEMENT & GOVERNANCE | 4% | 213333.3333
| Phase 2 project management | 100% | 213333.3333
| CONTINGENCY | 2% | 106666.6667
| Contingency reserve | 100% | 106666.6667
| SUBTOTAL (Tax-Exclusive, GHS) |  | 5333333.3333
| Tax (Effective Rate) |  | 1066666.6667
| TOTAL (Tax-Inclusive, GHS) |  | 6400000
| Check vs Assumptions Phase Total |  | OK

## Phase 3 - Marking-Fusion
PHASE 3 — Product Marking & Full Fusion
Months 12-18 ¦ GasGuard MarkChain rollout with the NPA's Petroleum Product Marking Scheme, full AI fusion-layer integration
| Phase Total (Tax-Exclusive, GHS) | 3333333.3333
| Effective Tax Rate | 20%
| Phase Total (Tax-Inclusive, GHS) | 4000000
| Cost Category / Line Item | Weight | Amount (Tax-Excl, GHS)
| HARDWARE & EQUIPMENT PROCUREMENT | 15% | 500000
| Product-marking / tracer dosing equipment | 100% | 500000
| SOFTWARE LICENSING & PLATFORM INTEGRATION | 35% | 1166666.6667
| GasGuard MarkChain digital custody audit trail | 50% | 583333.3333
| Full AI/ML fusion-layer integration & model refinement | 50% | 583333.3333
| PROFESSIONAL SERVICES & IMPLEMENTATION | 30% | 1000000
| NPA coordination & marking-scheme rollout | 40% | 400000
| Full-network fusion integration & testing | 60% | 600000
| TRAINING & KNOWLEDGE TRANSFER | 8% | 266666.6667
| Knowledge transfer & handover to GNGC operations team | 100% | 266666.6667
| PROJECT MANAGEMENT & GOVERNANCE | 7% | 233333.3333
| Phase 3 project management | 100% | 233333.3333
| CONTINGENCY | 5% | 166666.6667
| Contingency reserve | 100% | 166666.6667
| SUBTOTAL (Tax-Exclusive, GHS) |  | 3333333.3333
| Tax (Effective Rate) |  | 666666.6667
| TOTAL (Tax-Inclusive, GHS) |  | 4000000
| Check vs Assumptions Phase Total |  | OK

## Support-Subscription (Yr2+)
Year 2+ Annual Support & Subscription (Illustrative)
NOT part of the GHS 16,000,000 Phase 0-3 project total — a recommended recurring commercial structure per proposal Section 8.
| Cumulative Software Licensing Value (Tax-Exclusive, GHS) | 3993333.3333
| Annual Support Fee Rate (% of Software Licensing value) | 18%
| Annual Support Fee (Tax-Exclusive, GHS) | 718800
| Effective Tax Rate | 20%
| Annual Support Fee (Tax-Inclusive, GHS) | 862560
This fee is recommended to begin in Year 2, following Phase 1 go-live, and covers the GasGuard Fusion platform, dashboard, and AI/ML model maintenance across all deployed modules. Third-party hardware maintenance/renewal (fiber interrogators, satellite subscriptions, IoT device replacement) is separate and to be defined jointly during Phase 0, per proposal Section 8.