## 📊 Executive Summary
GHANA CHAMBER OF MINES MEMBER MANAGEMENT & REPORT AGGREGATION SYSTEM SOFTWARE DEVELOPMENT BUDGET
Fiscal Year 2025 – 2027 ¦ Prepared by: IT & Strategy Division ¦ Date: May 2025
Total 3-Year Investment (GHS) | Year 1 (Discovery & Build) |  |  | Year 2 (Deploy & Optimize) |  | Year 3 (Scale & Sustain)
1991150 | 706000 |  |  | 356000 |  | 175000
BUDGET BY PHASE |  |  |  |  | BUDGET BY COST CATEGORY
Phase | Yr 1 (GHS) | Yr 2 (GHS) | Yr 3 (GHS) | Total (GHS) | Category |  | Yr 1 | Yr 2 | Yr 3
Phase 1: Discovery & Planning | 63000 | 0 | 0 | 63000 | Personnel & Labour |  | 706000 | 356000 | 175000
Phase 2: System Architecture & Design | 107000 | 0 | 0 | 107000 | Software & Licences |  | 27000 | 0 | 0
Phase 3: Core Development | 375000 | 135000 | 0 | 510000 | Infrastructure & Cloud |  | 78000 | 152000 | 167000
Phase 4: Integration & Testing | 63000 | 28000 | 0 | 91000 | Training & Change Mgmt |  | 176000 | 65000 | 0
Phase 5: Deployment & Training | 98000 | 33000 | 0 | 131000 | Contingency (15%) |  | 139650 | 0 | 0
Phase 6: Support & Maintenance | 0 | 160000 | 175000 | 335000 | Other / Miscellaneous |  | 120000 | 38500 | 0
GRAND TOTAL | 706000 | 356000 | 175000 | 1237000 | TOTAL |  | 1246650 | 611500 | 342000
KEY ASSUMPTIONS & NOTES
1. All figures are in Ghana Cedis (GHS). USD equivalents available on the FX Assumptions tab.
2. Blue text = user-editable inputs; Black text = calculated values; Green text = cross-sheet links.
3. Personnel costs assume mixed team (2 senior devs, 3 mid devs, 1 BA, 1 PM, 1 QA, 1 DevOps) for Year 1.
4. A 15% contingency buffer is included in all years to absorb scope changes and risk events.
5. Cloud/infrastructure costs are based on AWS GovCloud equivalent pricing, scaled annually.
6. Training covers GCoM staff (est. 45 users) + member company super-users (est. 120 users).

## 💰 Budget Breakdown
GHANA CHAMBER OF MINES — MEMBER MANAGEMENT SYSTEM ¦ DETAILED BUDGET BREAKDOWN (GHS)
Blue = Input ¦ Black = Formula ¦ Green = Cross-sheet link ¦ Source: GCoM IT Strategy Plan 2025
LINE ITEM / DELIVERABLE | YEAR 1 — FY2025 |  | YEAR 2 — FY2026 |  | YEAR 3 — FY2027 |  | CONTINGENCY (15%) |  | 3-YEAR TOTAL (GHS)
| Labour (GHS) | Non-Labour (GHS) | Labour (GHS) | Non-Labour (GHS) | Labour (GHS) | Non-Labour (GHS) | Labour (GHS) | Non-Labour (GHS)
PHASE 1 — DISCOVERY & PLANNING (Months 1–3)
Requirements gathering & stakeholder workshops | 25000 | 5000 | 0 | 0 | 0 | 0 | 3750 | 750 | 34500
Current system audit & gap analysis | 18000 | 3000 | 0 | 0 | 0 | 0 | 2700 | 450 | 24150
Feasibility study & vendor evaluation | 12000 | 8000 | 0 | 0 | 0 | 0 | 1800 | 1200 | 23000
Project charter & governance setup | 8000 | 2000 | 0 | 0 | 0 | 0 | 1200 | 300 | 11500
PHASE 1 SUBTOTAL | 63000 | 18000 | 0 | 0 | 0 | 0 | 9450 | 2700 | 93150
PHASE 2 — SYSTEM ARCHITECTURE & DESIGN (Months 2–5)
System architecture design (cloud-native) | 32000 | 5000 | 0 | 0 | 0 | 0 | 4800 | 750 | 42550
Database schema design (member registry + reports) | 22000 | 2000 | 0 | 0 | 0 | 0 | 3300 | 300 | 27600
UI/UX wireframes & prototype | 18000 | 12000 | 0 | 0 | 0 | 0 | 2700 | 1800 | 34500
API & integration design | 20000 | 3000 | 0 | 0 | 0 | 0 | 3000 | 450 | 26450
Security architecture & data governance plan | 15000 | 5000 | 0 | 0 | 0 | 0 | 2250 | 750 | 23000
PHASE 2 SUBTOTAL | 107000 | 27000 | 0 | 0 | 0 | 0 | 16050 | 4050 | 154100
PHASE 3 — CORE DEVELOPMENT (Months 4–14)
Member registry & profile management module | 85000 | 15000 | 30000 | 5000 | 0 | 0 | 12750 | 2250 | 150000
Member onboarding portal & self-service | 60000 | 10000 | 20000 | 3000 | 0 | 0 | 9000 | 1500 | 103500
Subscription & dues management module | 45000 | 8000 | 15000 | 2000 | 0 | 0 | 6750 | 1200 | 77950
Report submission & aggregation engine | 90000 | 20000 | 35000 | 8000 | 0 | 0 | 13500 | 3000 | 169500
Dashboard & analytics module (BI layer) | 55000 | 25000 | 20000 | 10000 | 0 | 0 | 8250 | 3750 | 122000
Document management & compliance tracker | 40000 | 8000 | 15000 | 3000 | 0 | 0 | 6000 | 1200 | 73200
PHASE 3 SUBTOTAL | 375000 | 86000 | 135000 | 31000 | 0 | 0 | 56250 | 12900 | 696150
PHASE 4 — INTEGRATION & TESTING (Months 12–16)
System integration testing (SIT) | 28000 | 5000 | 12000 | 2000 | 0 | 0 | 4200 | 750 | 51950
User acceptance testing (UAT) with GCoM staff | 20000 | 3000 | 8000 | 1500 | 0 | 0 | 3000 | 450 | 35950
Performance & load testing | 15000 | 8000 | 8000 | 4000 | 0 | 0 | 2250 | 1200 | 38450
PHASE 4 SUBTOTAL | 63000 | 16000 | 28000 | 7500 | 0 | 0 | 9450 | 2400 | 126350
PHASE 5 — DEPLOYMENT & TRAINING (Months 16–20)
Cloud infrastructure setup & go-live | 20000 | 45000 | 5000 | 15000 | 0 | 0 | 3000 | 6750 | 94750
Data migration from legacy systems | 35000 | 10000 | 10000 | 5000 | 0 | 0 | 5250 | 1500 | 66750
End-user training — GCoM staff (45 users) | 18000 | 8000 | 8000 | 4000 | 0 | 0 | 2700 | 1200 | 41900
Member company super-user training (120 users) | 25000 | 15000 | 10000 | 8000 | 0 | 0 | 3750 | 2250 | 64000
PHASE 5 SUBTOTAL | 98000 | 78000 | 33000 | 32000 | 0 | 0 | 14700 | 11700 | 267400
PHASE 6 — ONGOING SUPPORT & MAINTENANCE (Year 2–3, recurring)
Application support & helpdesk | 0 | 0 | 60000 | 12000 | 65000 | 12000 | 0 | 0 | 149000
Annual software licence renewals | 0 | 0 | 5000 | 35000 | 5000 | 40000 | 0 | 0 | 85000
Cloud hosting & infrastructure (annual) | 0 | 0 | 5000 | 80000 | 5000 | 90000 | 0 | 0 | 180000
Feature enhancements & change requests | 0 | 0 | 70000 | 15000 | 80000 | 15000 | 0 | 0 | 180000
Security patches & compliance updates | 0 | 0 | 20000 | 10000 | 20000 | 10000 | 0 | 0 | 60000
PHASE 6 SUBTOTAL | 0 | 0 | 160000 | 152000 | 175000 | 167000 | 0 | 0 | 654000
GRAND TOTAL — ALL PHASES | 706000 | 225000 | 356000 | 222500 | 175000 | 167000 | 105900 | 33750 | 1991150
Personnel & Labour | 706000 |  | 356000 |  | 175000
Software & Licences | 27000 |  | 0 |  | 0
Infrastructure & Cloud | 78000 |  | 152000 |  | 167000
Training & Change Mgmt | 176000 |  | 65000 |  | 0
Contingency (15%) | 139650 |  | 0 |  | 0
Other / Miscellaneous | 120000 |  | 38500 |  | 0

## 👥 Staffing Plan
GHANA CHAMBER OF MINES — SOFTWARE PROJECT STAFFING PLAN & RATE CARD (GHS)
Role | Engagement Type | Monthly Rate (GHS) | Yr1 Months | Yr1 Cost (GHS) | Yr2 Months | Yr2 Cost (GHS) | Yr3 Months | Yr3 Cost (GHS) | Count | FTE Equiv. | Notes
Project Manager | Fixed-term contract | 18000 | 18 | 324000 | 12 | 216000 | 6 | 108000 | 1 | 0.5 | GCoM-side PM; oversees delivery
Business Analyst | Fixed-term contract | 14000 | 14 | 196000 | 8 | 112000 | 4 | 56000 | 1 | 0.5 | Requirements, UAT, documentation
Solution Architect | Consultancy | 25000 | 10 | 250000 | 6 | 150000 | 3 | 75000 | 1 | 0.5 | Cloud-native; AWS or Azure certified
Senior Full-Stack Developer | Fixed-term contract | 22000 | 18 | 792000 | 18 | 792000 | 18 | 792000 | 2 | 1 | React/Node or Django stack
Mid Full-Stack Developer | Fixed-term contract | 15000 | 16 | 720000 | 16 | 720000 | 16 | 720000 | 3 | 1.5 | Feature dev & integration
Mobile Developer (iOS/Android) | Fixed-term contract | 18000 | 12 | 216000 | 12 | 216000 | 12 | 216000 | 1 | 0.5 | Member mobile portal
UI/UX Designer | Consultancy | 12000 | 8 | 96000 | 4 | 48000 | 2 | 24000 | 1 | 0.5 | Figma; design system ownership
Data Engineer / BI Developer | Fixed-term contract | 18000 | 14 | 252000 | 14 | 252000 | 14 | 252000 | 1 | 0.5 | Report aggregation & dashboards
QA / Test Engineer | Fixed-term contract | 12000 | 16 | 192000 | 12 | 144000 | 12 | 144000 | 1 | 0.5 | Automated + manual testing
DevOps / Cloud Engineer | Fixed-term contract | 20000 | 18 | 360000 | 18 | 360000 | 18 | 360000 | 1 | 0.5 | CI/CD, security, monitoring
Database Administrator | Part-time | 10000 | 12 | 120000 | 12 | 120000 | 12 | 120000 | 1 | 0.5 | PostgreSQL / MongoDB
Cybersecurity Consultant | Consultancy | 22000 | 6 | 132000 | 4 | 88000 | 2 | 44000 | 1 | 0.5 | Pen-testing, compliance (ISO 27001)
Change Management Specialist | Consultancy | 14000 | 6 | 84000 | 3 | 42000 | 2 | 28000 | 1 | 0.5 | Training & adoption
Technical Writer | Freelance | 8000 | 8 | 64000 | 4 | 32000 | 2 | 16000 | 1 | 0.5 | User manuals, API docs
Helpdesk / Support Analyst | Permanent hire | 8000 | 0 | 0 | 12 | 192000 | 12 | 192000 | 2 | 1 | Operational support Year 2+
TOTAL PERSONNEL COST |  |  |  | 3798000 |  | 3484000 |  | 3147000

## 📅 Timeline & Milestones
GHANA CHAMBER OF MINES — PROJECT TIMELINE & MILESTONES (36 MONTHS)
PHASE / MILESTONE | [6 empty] | YEAR 1 — FY2025 | [7 empty] | YEAR 2 — FY2026 | [7 empty] | YEAR 3 — FY2027
|  | Due Date | Budget (GHS) | Owner | Status | Risk Level | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36
PHASE 1: DISCOVERY & PLANNING
Kick-off & stakeholder alignment | Aug 2025 | 15000 | PM / BA | Not Started | Low
Requirements & gap analysis complete | Sep 2025 | 28000 | BA | Not Started | Medium
Procurement & vendor selection done | Oct 2025 | 12000 | Procurement | Not Started | Medium
PHASE 2: ARCHITECTURE & DESIGN
System architecture approved | Nov 2025 | 40000 | Architect | Not Started | Medium
UI/UX prototype signed off | Dec 2025 | 30000 | UX / PM | Not Started | Low
PHASE 3: CORE DEVELOPMENT
Member registry module live (Beta) | Feb 2026 | 120000 | Dev Lead | Not Started | High
Report aggregation engine complete | May 2026 | 150000 | Data Eng | Not Started | High
BI dashboard & analytics ready | Jul 2026 | 90000 | Dev Lead | Not Started | Medium
PHASE 4: INTEGRATION & TESTING
SIT & UAT cycles complete | Sep 2026 | 55000 | QA / PM | Not Started | Medium
Security pen-test passed | Oct 2026 | 35000 | CyberSec | Not Started | High
PHASE 5: DEPLOYMENT & TRAINING
Go-live (Production launch) | Jan 2027 | 80000 | DevOps / PM | Not Started | High
All users trained & onboarded | Mar 2027 | 60000 | Change Mgmt | Not Started | Medium
PHASE 6: SUPPORT & MAINTENANCE
Year 2 feature release 1 | Jul 2027 | 85000 | Dev Lead | Not Started | Low
Annual security & compliance review | Jul 2027 | 30000 | CyberSec | Not Started | Medium
Year 3 feature release 2 | Jan 2028 | 95000 | Dev Lead | Not Started | Low
Project closure & handover | Jun 2028 | 20000 | PM | Not Started | Low

## ⚠️ Risk Register
GHANA CHAMBER OF MINES — PROJECT RISK REGISTER
ID | Risk Description | Category | Likelihood (1–5) | Impact (1–5) | Risk Score (L×I) | Mitigation Strategy | Contingency Action | Owner | Budget Impact (GHS)
R01 | Scope creep due to evolving member requirements | Scope | 3 | 4 | 12 | Agile delivery with change control board; fixed sprint scope | Activate contingency budget; defer non-critical features | PM | 85000
R02 | Key developer attrition during build phase | HR / Talent | 2 | 5 | 10 | Competitive market rates; knowledge-transfer protocols | Maintain talent pipeline; use bench contractors | Dev Lead | 120000
R03 | GHS/USD exchange rate volatility (imported tools) | Financial | 4 | 3 | 12 | Hedge with GHS pricing clauses in contracts | Activate FX buffer in contingency fund | Finance | 60000
R04 | Data migration errors from legacy systems | Technical | 3 | 4 | 12 | Parallel-run migration; automated reconciliation scripts | Roll back to legacy; manual data correction sprint | DBA | 50000
R05 | Low user adoption by member companies | Change | 3 | 4 | 12 | Early-adopter pilot; champion network; UX research | Extended training; enhanced helpdesk support | Change Mgmt | 70000
R06 | Cybersecurity breach / data leak | Security | 2 | 5 | 10 | ISO 27001 alignment; penetration testing; MFA enforced | Incident response plan; regulatory notification | CyberSec | 200000
R07 | Cloud provider outage (AWS / GCP) | Infrastructure | 2 | 4 | 8 | Multi-AZ deployment; automated failover | Activate DR site; communicate SLA breach | DevOps | 40000
R08 | Regulatory / legal compliance gaps (PNDCL 153) | Legal | 2 | 4 | 8 | Legal review at each phase; GDPA compliance checklist | Engage legal counsel; architecture rework | Legal / PM | 55000
R09 | Budget overrun beyond 15% contingency | Financial | 2 | 5 | 10 | Monthly burn-rate reviews; earned-value reporting | Seek supplementary board approval | PM / Finance | 150000
R10 | Integration failure with existing GCoM ERP | Technical | 3 | 3 | 9 | API-first design; sandbox integration testing from Month 2 | Maintain interim manual process | Dev Lead / BA | 45000

## 🔧 Assumptions & FX
GHANA CHAMBER OF MINES — KEY ASSUMPTIONS & FX REFERENCE
FX & CURRENCY ASSUMPTIONS
GHS / USD Exchange Rate (budget rate) | 15.5 | Editable Input | Source: Bank of Ghana, May 2025 average
GHS / EUR Exchange Rate (budget rate) | 16.8 | Editable Input | Source: Bank of Ghana, May 2025 average
GHS / GBP Exchange Rate (budget rate) | 19.6 | Editable Input | Source: Bank of Ghana, May 2025 average
Annual FX volatility buffer (%) | 8% | Editable Input | 8% buffer applied to foreign-currency items
INFLATION & ESCALATION
Ghana CPI / annual inflation assumption | 23% | Editable Input | Source: Ghana Statistical Service, 2025 forecast
IT salary escalation (annual) | 15% | Editable Input | Competitive tech market in Ghana & West Africa
Cloud cost escalation (annual) | 5% | Editable Input | AWS pricing trend; offset by reserved instances
General cost contingency buffer | 15% | Editable Input | Applied to all line items; see Budget Breakdown
PROJECT PARAMETERS
Total project duration (months) | 36 | Editable Input | FY2025 – FY2027
Total GCoM internal staff (end users) | 45 | Editable Input | Accra HQ + regional offices
Member company super-users | 120 | Editable Input | Est. 3 super-users × 40 member companies
Number of member companies (current) | 40 | Editable Input | Source: GCoM Membership Register 2025
Sprint duration (weeks) | 2 | Editable Input | Agile/Scrum delivery methodology
UAT sign-off period (weeks) | 3 | Editable Input | Per major module; requires GCoM Director sign-off
TECHNOLOGY ASSUMPTIONS
Primary cloud provider | AWS (af-south-1) | Editable Input | Cape Town region; lowest latency for Ghana
Database technology | PostgreSQL + MongoDB | Editable Input | Relational + document store for reports
Frontend framework | React 18 + TypeScript | Editable Input | Progressive Web App + mobile-responsive
Backend framework | Node.js / Django REST | Editable Input | Microservices architecture
Authentication | OAuth2 + MFA (Okta) | Editable Input | Single sign-on for GCoM and members
Reporting layer | Apache Superset / Power BI | Editable Input | Self-service BI for GCoM management
CI/CD pipeline | GitHub Actions + Terraform | Editable Input | Infrastructure as code
Data backup frequency | Daily + real-time replication | Editable Input | RPO < 1 hr; RTO < 4 hrs