GHANA GOLD BOARD (GOLDBOD)

Traceability & Assurance System (TAS)

INDICATIVE PROJECT BUDGET — EXPRESSION OF INTEREST

REF: GR/GGB/TS/NCT/042/2026  |  April 2026

| Contract Duration | 18 Months (6 Months Implementation + 12 Months Stabilisation) |
| --- | --- |
| Procurement Method | Quality & Cost Based Selection (QCBS) |
| Regulatory Framework | Public Procurement Act, 2003 (Act 663, as amended) |
| Primary Currency | USD — with GHS equivalent at 1 USD = 13 GHS (indicative, April 2026) |
| Total Project Budget | USD 11,325,000 ¦ GHS 147,225,000 |
| Budget Date | April 2026 |
| Contract Reference | GR/GGB/TS/NCT/042/2026 |

# KEY ASSUMPTIONS & CONSTRAINTS

The following assumptions underpin all cost estimates within this budget. Any material deviation from these parameters — particularly the exchange rate, project scope, or statutory obligations — will require a formal change request and budget revision.

## Financial & Currency Assumptions

- Exchange Rate: 1 USD = 13 GHS (indicative as at April 2026). The rate will be locked at contract signing; all GHS figures herein are illustrative conversions.

- Exchange Rate Variance: A ±5% foreign exchange buffer is built into the contingency provision to cover GHS depreciation risk.

- Ghana Inflation: ~20% p.a. local inflation is assumed. An escalation clause will be negotiated for GHS-denominated costs beyond Month 6.

- Cloud Cost Inflation: ±5% year-on-year variance assumed; reserved instance pricing to be secured at contract commencement.

- All estimates are exclusive of VAT (15% applicable on locally procured goods and services) and statutory withholding tax on foreign service payments.

- Employer PAYE, SSNIT (13%) and Tier 2 Pension (5%) contributions on Ghanaian national salaries are included in personnel costs.

- A 10% performance bond/bank guarantee is required at contract signing.

## Project & Scope Assumptions

- Contract start is assumed Q2 2026; Phase 1 implementation begins within one week of contract signing.

- Total project duration is 18 months: 6 months of implementation followed by 12 months of stabilisation and support.

- No material scope changes are assumed. All change requests will be priced separately per an agreed change control schedule.

- GoldBod will facilitate introductions and system access to all six (6) government agency integration partners within Month 1.

- The NIA Ghana Card identity verification API will be available and accessible by contract start.

- A hybrid cloud architecture is assumed with primary data stored in a Ghana-based data centre, in compliance with the Data Protection Act 843.

- MTN / Vodafone 4G coverage is assumed at all operational sites; satellite fallback is provisioned for remote areas.

- Hardware import duties are estimated at 20% of CIF value; relief via a government waiver will be pursued where available.

## Compliance & Governance Assumptions

- A minimum of 60% Ghanaian personnel by headcount and 40% local sub-contracting spend is committed in line with local content policy.

- All procurement sub-thresholds comply with the Public Procurement Act, 2003 (Act 663, as amended).

- Milestone-based payment terms apply; invoices are to be settled within 30 days of milestone sign-off by GoldBod.

- Full source code, documentation, and intellectual property will be assigned to GoldBod upon receipt of final payment.

- A 12-month post-handover warranty commences at the conclusion of the stabilisation phase (Month 18).

# EXECUTIVE BUDGET SUMMARY

The table below presents the consolidated budget across all 16 cost categories. The total project investment of USD 11,325,000 (GHS 147,225,000) covers the full 18-month engagement from design through to stabilisation and handover.

| Cost Category | USD Amount | GHS Amount | % of Total |
| --- | --- | --- | --- |
| 1. Personnel & HR Costs | $3,250,000 | GHS 42,250,000 | 28.7% |
| 2. Software Development | $1,980,000 | GHS 25,740,000 | 17.5% |
| 3. Blockchain Infrastructure | $820,000 | GHS 10,660,000 | 7.2% |
| 4. Cloud & Hosting (18 months) | $540,000 | GHS 7,020,000 | 4.8% |
| 5. Software Licences & Tools | $310,000 | GHS 3,380,000 | 2.7% |
| 6. Hardware & Field Equipment | $680,000 | GHS 8,840,000 | 6.0% |
| 7. Systems Integration (6 Agencies) | $640,000 | GHS 8,320,000 | 5.7% |
| 8. Testing & Quality Assurance | $290,000 | GHS 4,495,000 | 2.6% |
| 9. Training & Capacity Building | $420,000 | GHS 5,460,000 | 3.7% |
| 10. Compliance & Legal | $180,000 | GHS 2,340,000 | 1.6% |
| 11. Project Management & PMO | $380,000 | GHS 4,940,000 | 3.4% |
| 12. Pilot Programme | $175,000 | GHS 2,275,000 | 1.5% |
| 13. National Deployment | $240,000 | GHS 3,120,000 | 2.1% |
| 14. Stabilisation & Support (12 Mths) | $750,000 | GHS 9,750,000 | 6.6% |
| 15. Documentation & Deliverables | $95,000 | GHS 1,235,000 | 0.8% |
| 16. Contingency (10%) | $575,000 | GHS 7,475,000 | 5.1% |
| TOTAL PROJECT BUDGET | USD 11,325,000 | GHS 147,225,000 | 100.0% |

# DETAILED BUDGET BREAKDOWN

## 1. System Design & Architecture

The design and architecture phase establishes the full technical blueprint for the TAS. This includes end-to-end blockchain architecture (Hyperledger Fabric), AI analytics engine design, security threat modelling, and comprehensive stakeholder consultation. Robust upfront design is critical to containing downstream development costs and rework.

| Item / Deliverable | Description | USD | GHS |
| --- | --- | --- | --- |
| Requirements Analysis & Stakeholder Consultations | Workshops, field assessments, facilitated requirements sessions across all user groups and regulatory bodies | $275,000 | GHS 3,575,000 |
| System Architecture Design & Technical Blueprint | End-to-end TAS architecture (Blockchain + AI analytics + mobile + API layers) | $85,000 | GHS 1,105,000 |
| Blockchain Network Architecture Specification | Hyperledger Fabric permissioned network design, node topology, consensus configuration | $55,000 | GHS 715,000 |
| UX Research & Wireframing (All User Roles) | Web and mobile interface design across 8 defined user roles | $45,000 | GHS 585,000 |
| Data Model & Database Schema Design | Relational and on-chain data model design | $25,000 | GHS 325,000 |
| Security Architecture & Threat Modelling | Cybersecurity framework, threat model, penetration test plan | $35,000 | GHS 455,000 |
| Integration Architecture & API Design (6 Agencies) | API specification for all 6 government agency integrations | $40,000 | GHS 520,000 |
| Sub-Total |  | $560,000 | GHS 7,280,000 |

## 2. Software Development

Software development constitutes the largest single investment category, reflecting the complexity of a multi-phase, enterprise-grade blockchain platform. Development is structured across six phases — from core platform build through to national go-live — with ongoing stabilisation sprints over the 12-month support period.

| Item / Deliverable | Description | USD | GHS |
| --- | --- | --- | --- |
| Core Backend API Development (Node.js / Python) | RESTful and GraphQL APIs powering all platform modules | $150,000 | GHS 1,950,000 |
| Blockchain Network Setup — Hyperledger Fabric | Permissioned network configuration, smart contract deployment, chaincode development & auditing | $215,000 | GHS 2,795,000 |
| Supply Chain, Chain-of-Custody & Provenance Modules | Core gold traceability ledger modules including assay recording and digital certificate generation | $140,000 | GHS 1,820,000 |
| KYC / AML Module | Identity verification, compliance checks, Ghana Card API integration | $70,000 | GHS 910,000 |
| Mobile Applications (Android & iOS) | Field officer and miner apps with offline mode, GPS, QR/NFC/RFID scanner and digital signature | $265,000 | GHS 3,445,000 |
| Admin Dashboard, Analytics Portal & BI Reporting | Web-based management portal and OECD/LBMA/FIC-compliant reporting module | $135,000 | GHS 1,755,000 |
| DevOps, CI/CD & Infrastructure-as-Code | Kubernetes/Docker container orchestration, automated deployment and monitoring | $143,000 | GHS 1,859,000 |
| Pilot & National Rollout Development | Site-specific configuration, data migration, go-live support and hotfix sprints | $205,000 | GHS 2,665,000 |
| Stabilisation & Ongoing Development (Months 7–18) | Quarterly feature enhancement sprints, patch management, regulatory updates | $180,000 | GHS 2,340,000 |
| Sub-Total |  | $1,503,000 | GHS 19,539,000 |

## 3. Infrastructure, Cloud & Licences

Infrastructure costs cover cloud hosting (primary Ghana-based data centre plus disaster recovery), blockchain node infrastructure, cybersecurity tooling, and all required software licences for the 18-month engagement. Reserved instance pricing will be secured at contract commencement to control year-on-year cost escalation.

| Item / Deliverable | Description | USD | GHS |
| --- | --- | --- | --- |
| Hyperledger Fabric Platform Support & SLA | Enterprise SLA and professional support for the blockchain network | $270,000 | GHS 3,510,000 |
| Cloud Hosting — Primary & DR (Ghana-based) | Compute, storage and networking across production, UAT and staging environments | $180,000 | GHS 2,340,000 |
| Cloud Hosting — Disaster Recovery (International CDN) | Geo-redundant failover and content delivery infrastructure | $90,000 | GHS 1,170,000 |
| Cybersecurity Infrastructure | Firewalls, intrusion detection, SIEM, encryption tooling and monitoring | $100,000 | GHS 1,300,000 |
| Software Licences (Dev Tools, Analytics, BI, LMS) | All third-party software licences required for the 18-month project | $310,000 | GHS 3,380,000 |
| Domain, SSL Certificates & API Gateway | Domain registration, wildcard SSL, API management gateway | $30,000 | GHS 390,000 |
| Sub-Total |  | $980,000 | GHS 12,740,000 |

## 4. Hardware & Field Equipment

Hardware procurement covers rugged field devices for ASM mine-site officers, IoT tracking sensors for gold parcels, assay and weight-recording equipment, and enterprise hardware for GoldBod regional offices. Import duties (~20% CIF) are included; relief via government waiver will be pursued.

| Item / Deliverable | Description | USD | GHS |
| --- | --- | --- | --- |
| Rugged Android Smartphones for Field Officers (×120) | IP-rated field devices with pre-loaded TAS mobile app | $42,000 | GHS 546,000 |
| Tablets for Regional Office Supervisors (×40) | Enterprise-grade tablets for supervisory dashboards | $28,000 | GHS 364,000 |
| Laptop / Desktop Workstations for GoldBod Offices (×30) | Office-grade workstations for back-office staff | $45,000 | GHS 585,000 |
| IoT Sensors & Gold Tracking Devices | NFC/RFID tags and IoT sensors for gold parcel tracking | $250,000 | GHS 3,250,000 |
| Assay & Weight Recording Equipment | Calibrated scales, portable assay kits and data-capture peripherals | $85,000 | GHS 1,105,000 |
| Network & Connectivity Equipment (Field Sites) | Routers, switches and satellite uplink devices for remote sites | $80,000 | GHS 1,040,000 |
| Server Hardware (On-Premise Backup — GoldBod HQ) | On-premise server for local redundancy and offline resilience | $70,000 | GHS 910,000 |
| Hardware Import Duties & Logistics | Estimated 20% import duty on CIF value plus inland logistics | $80,000 | GHS 1,040,000 |
| Sub-Total |  | $680,000 | GHS 8,840,000 |

## 5. Systems Integration

The TAS must integrate with six government agencies to deliver a fully verified chain-of-custody. Integration costs cover API development, testing, data-exchange agreements and the ongoing maintenance of each agency connection. GoldBod will facilitate formal introductions and system access within Month 1.

| Item / Deliverable | Description | USD | GHS |
| --- | --- | --- | --- |
| Minerals Commission — Licensing & Cadastre API | Real-time licence verification and mining cadastre data exchange | $45,000 | GHS 585,000 |
| Ghana Revenue Authority — Customs Export Verification | Automated export certification and tax compliance validation | $40,000 | GHS 520,000 |
| Bank of Ghana — Gold Purchase & FX Declaration | Integration with BoG gold purchasing window and FX reporting | $50,000 | GHS 650,000 |
| Financial Intelligence Centre — AML/CFT Reporting | Automated STR/CTR submission and beneficial ownership data exchange | $55,000 | GHS 715,000 |
| Environmental Protection Agency — Compliance Module | Mine site environmental certification and permit verification | $35,000 | GHS 455,000 |
| NIA — Ghana Card Identity Verification API | KYC identity verification for all registered supply chain participants | $40,000 | GHS 520,000 |
| Integration Testing & UAT (All Agencies) | End-to-end integration testing, agency UAT support and sign-off | $75,000 | GHS 975,000 |
| Ongoing API Maintenance (Months 7–18) | API version management, agency system updates and change coordination | $60,000 | GHS 780,000 |
| Sub-Total |  | $400,000 | GHS 5,200,000 |

## 6. Testing & Quality Assurance

A dedicated QA workstream ensures the platform meets GoldBod's security, performance and regulatory requirements before go-live. This includes functional testing, security audits, independent penetration testing, user acceptance testing (UAT) with all six agencies, and load testing at full national rollout scale.

| Item / Deliverable | Description | USD | GHS |
| --- | --- | --- | --- |
| Test Environment Hosting — UAT + Staging (6 months) | Dedicated cloud environments for QA and UAT activities | $30,000 | GHS 390,000 |
| Functional & Regression Testing (All Modules) | Structured test plans and execution across all platform modules | $60,000 | GHS 780,000 |
| Security Penetration Testing (3 rounds) | Independent pen-test at Phase 2, Pilot, and Pre-Go-Live | $40,000 | GHS 520,000 |
| Performance & Load Testing | Load simulation at 1,800+ concurrent ASM operations | $25,000 | GHS 325,000 |
| User Acceptance Testing (6 Agency Partners) | Facilitated UAT sessions with all government integration partners | $45,000 | GHS 585,000 |
| Defect Management & Bug Fix Tracking | Defect tracking platform, triage and resolution SLAs | $20,000 | GHS 260,000 |
| Test Automation Framework | Automated regression test suite for CI/CD pipeline | $35,000 | GHS 455,000 |
| VAPT Report & Remediation | Vulnerability assessment and penetration test remediation cycle | $35,000 | GHS 455,000 |
| Sub-Total |  | $290,000 | GHS 4,495,000 |

## 7. Training & Capacity Building

A structured training programme ensures all user groups — from GoldBod officials and field officers to regulators and mining company personnel — are equipped to operate the TAS confidently. A train-the-trainer model is employed to maximise national rollout efficiency and transfer sustainable capability to GoldBod.

| Item / Deliverable | Description | USD | GHS |
| --- | --- | --- | --- |
| Training Needs Assessment & Skills Gap Analysis | Baseline assessment across all 8 user roles | $12,000 | GHS 156,000 |
| Curriculum Design & Training Materials (All Roles) | Comprehensive course materials, facilitator guides and assessments | $30,000 | GHS 390,000 |
| E-Learning / LMS Development & Content | Online self-paced modules hosted on a GoldBod-branded LMS | $35,000 | GHS 455,000 |
| Train-the-Trainer Programme (Regional Leads) | Intensive training for 30 regional training facilitators | $40,000 | GHS 520,000 |
| Technical Training — GoldBod IT & Admin Staff | System administration, data management and platform governance | $30,000 | GHS 390,000 |
| Regulator & Government Agency Training (6 Agencies) | Agency-specific workshops and user acceptance briefings | $45,000 | GHS 585,000 |
| Field Officer Training (National Rollout) | Cascaded field training across approximately 1,800 ASM sites | $80,000 | GHS 1,040,000 |
| Mining Company & Exporter Training | Platform orientation for large-scale mines and gold export companies | $40,000 | GHS 520,000 |
| Post-Go-Live Refresher & Help Desk Knowledge Base | Refresher sessions and self-service knowledge base content | $20,000 | GHS 260,000 |
| Training Evaluation & Competency Assessment | Post-training assessment and competency certification | $13,000 | GHS 169,000 |
| Sub-Total |  | $345,000 | GHS 4,485,000 |

## 8. Project Management, PMO & Governance

A dedicated Project Management Office (PMO) provides end-to-end programme governance, risk management, stakeholder reporting and change control across the full 18-month engagement. The PMO operates from GoldBod-hosted offices and maintains weekly steering committee reporting.

| Item / Deliverable | Description | USD | GHS |
| --- | --- | --- | --- |
| PMO Setup, Office & Management Tools | Office fit-out, project management software (MS Project / Smartsheet) and collaboration tools | $75,000 | GHS 975,000 |
| Programme Manager (18 months) | Senior PM with blockchain/government programme experience | $180,000 | GHS 2,340,000 |
| Deputy PM & Project Coordinator (18 months) | Supporting PM functions and administrative coordination | $225,000 | GHS 2,925,000 |
| Financial Manager / Project Controller (18 months) | Budget tracking, invoice management and financial reporting | $117,000 | GHS 1,521,000 |
| Risk Management & Quality Assurance | Risk register management, quality audits and mitigation reporting | $40,000 | GHS 520,000 |
| Steering Committee & Stakeholder Reporting | Monthly executive dashboards, progress reports and ministerial briefings | $35,000 | GHS 455,000 |
| Legal & Compliance Oversight | Contract management, regulatory alignment and IP documentation | $51,000 | GHS 663,000 |
| Change Control & Configuration Management | Formal change request processing, version control governance | $25,000 | GHS 325,000 |
| Sub-Total |  | $748,000 | GHS 9,724,000 |

## 9. Compliance, Legal & Regulatory

Regulatory compliance costs ensure the TAS is fully aligned with Ghana's data protection legislation (Act 843), AML/CFT obligations under the FIC Act, and international standards (OECD Due Diligence Guidance, LBMA Responsible Gold). These are non-negotiable regulatory requirements.

| Item / Deliverable | Description | USD | GHS |
| --- | --- | --- | --- |
| Data Protection Act 843 — DPIA & Privacy Impact Assessment | Structured DPIA, data processing agreements and DPA registration | $12,000 | GHS 156,000 |
| AML/CFT Compliance Framework Design | Risk-based AML/CFT programme aligned to FIC Act requirements | $25,000 | GHS 325,000 |
| OECD & LBMA Due Diligence Compliance Design | Responsible gold guidance implementation and supply chain due diligence framework | $20,000 | GHS 260,000 |
| Legal Drafting — IP, Source Code & Service Agreements | IP assignment deed, SLA, NDA and all project legal instruments | $30,000 | GHS 390,000 |
| Regulatory Engagement — Minerals Commission & EPA | Formal regulatory liaison, permit applications and compliance filing | $20,000 | GHS 260,000 |
| Cybersecurity Compliance & ISO 27001 Alignment | Information security management system design and gap assessment | $30,000 | GHS 390,000 |
| External Legal Counsel (Contract Disputes, IP) | Retainer for external legal advisory throughout the project | $18,000 | GHS 234,000 |
| Compliance Audits (2 × annual) | Independent compliance audits at Month 9 and Month 18 | $25,000 | GHS 325,000 |
| Sub-Total |  | $180,000 | GHS 2,340,000 |

## 10. Documentation & Deliverables

All technical deliverables will be professionally documented in line with GoldBod's knowledge management requirements and international technical writing standards. Full documentation, source code repositories and operational manuals are included in the IP assignment to GoldBod.

| Item / Deliverable | Description | USD | GHS |
| --- | --- | --- | --- |
| System Architecture & Design Documentation | System Design Document (SDD), architecture diagrams and data dictionaries | $13,000 | GHS 169,000 |
| Technical Operations Manual | Platform administration, deployment, backup and recovery procedures | $10,000 | GHS 130,000 |
| User Guides & Quick Reference Manuals (All Roles) | Role-specific user guides for all 8 platform user groups | $12,000 | GHS 156,000 |
| API Documentation & Developer Guides | OpenAPI specifications, integration guides for all 6 agency integrations | $8,000 | GHS 104,000 |
| Training & E-Learning Content | Final training materials, presentations and LMS content packs | $12,000 | GHS 156,000 |
| Compliance & Audit Reports | DPIA report, security audit reports, UAT sign-off documentation | $10,000 | GHS 130,000 |
| Project Closure & Handover Report | Final lessons-learned report, warranty documentation and IP transfer pack | $15,000 | GHS 195,000 |
| Source Code Repository & Release Notes | Annotated source code repository, release history and version documentation | $15,000 | GHS 195,000 |
| Sub-Total |  | $95,000 | GHS 1,235,000 |

# SECTION 1 — PERSONNEL & HR COSTS

Personnel and human resource costs represent the largest single budget category at USD 3,250,000 (28.7% of total). The team is structured across eight functional sub-teams covering implementation, QA, integration, training, project management, compliance and post-go-live stabilisation. A minimum of 60% Ghanaian nationals by headcount is committed, with statutory on-costs (SSNIT, Tier 2, PAYE) fully included.

A. Technical Development Team (Implementation Phase)

| Role / Position | # | Mths | Rate / Month (USD) | Total (USD) | Total (GHS) |
| --- | --- | --- | --- | --- | --- |
| Blockchain Architect / Lead Developer | 1 | 8 | $12,000 | $96,000 | GHS 1,248,000 |
| Senior Backend Developer (Blockchain) | 2 | 6 | $9,000 | $108,000 | GHS 1,404,000 |
| Senior Backend Developer (API / Core Platform) | 2 | 6 | $8,500 | $102,000 | GHS 1,326,000 |
| Frontend Developer (Web Portal) | 2 | 6 | $7,000 | $84,000 | GHS 1,092,000 |
| Mobile App Developer (Android & iOS) | 2 | 6 | $7,500 | $90,000 | GHS 1,170,000 |
| Smart Contract Developer | 1 | 5 | $9,500 | $47,500 | GHS 617,500 |
| DevOps / Cloud Engineer | 2 | 7 | $8,000 | $112,000 | GHS 1,456,000 |
| Database Administrator | 1 | 6 | $7,000 | $42,000 | GHS 546,000 |
| Cybersecurity / Security Engineer | 1 | 6 | $8,500 | $51,000 | GHS 663,000 |
| Sub-Total: A. Technical Development Team (Implementation Phase) | $732,500 | GHS 9,522,500 |

B. QA & Testing Team

| Role / Position | # | Mths | Rate / Month (USD) | Total (USD) | Total (GHS) |
| --- | --- | --- | --- | --- | --- |
| QA Lead / Test Manager | 1 | 5 | $7,500 | $37,500 | GHS 487,500 |
| QA Engineer / Functional Tester | 3 | 5 | $5,500 | $82,500 | GHS 1,072,500 |
| Test Automation Engineer | 1 | 4 | $6,500 | $26,000 | GHS 338,000 |
| Penetration Tester / Security Auditor | 1 | 2 | $8,000 | $16,000 | GHS 208,000 |
| Sub-Total: B. QA & Testing Team | $162,000 | GHS 2,106,000 |

C. UI/UX Design & Business Analysis

| Role / Position | # | Mths | Rate / Month (USD) | Total (USD) | Total (GHS) |
| --- | --- | --- | --- | --- | --- |
| Lead UI/UX Designer | 1 | 5 | $7,000 | $35,000 | GHS 455,000 |
| Business Analyst (Gold Supply Chain) | 2 | 6 | $7,000 | $84,000 | GHS 1,092,000 |
| Requirements Engineer | 1 | 4 | $6,000 | $24,000 | GHS 312,000 |
| Domain Expert — AML/CFT Compliance | 1 | 4 | $9,000 | $36,000 | GHS 468,000 |
| Sub-Total: C. UI/UX Design & Business Analysis | $179,000 | GHS 2,327,000 |

D. Integration & Data Specialists

| Role / Position | # | Mths | Rate / Month (USD) | Total (USD) | Total (GHS) |
| --- | --- | --- | --- | --- | --- |
| Integration Architect | 1 | 5 | $9,000 | $45,000 | GHS 585,000 |
| API Developer / Integration Engineer | 2 | 5 | $7,000 | $70,000 | GHS 910,000 |
| Data Engineer | 1 | 6 | $7,000 | $42,000 | GHS 546,000 |
| Data Scientist / Analytics Specialist | 1 | 4 | $7,500 | $30,000 | GHS 390,000 |
| Sub-Total: D. Integration & Data Specialists | $187,000 | GHS 2,431,000 |

E. Training & Change Management

| Role / Position | # | Mths | Rate / Month (USD) | Total (USD) | Total (GHS) |
| --- | --- | --- | --- | --- | --- |
| Training Programme Manager | 1 | 6 | $6,500 | $39,000 | GHS 507,000 |
| Field Training Specialist (Regional) | 4 | 4 | $4,500 | $72,000 | GHS 936,000 |
| Change Management Consultant | 1 | 4 | $8,000 | $32,000 | GHS 416,000 |
| Technical Writer / Documentation Specialist | 1 | 6 | $5,000 | $30,000 | GHS 390,000 |
| Sub-Total: E. Training & Change Management | $173,000 | GHS 2,249,000 |

F. Project Management Office (Full 18 Months)

| Role / Position | # | Mths | Rate / Month (USD) | Total (USD) | Total (GHS) |
| --- | --- | --- | --- | --- | --- |
| Project Manager | 1 | 18 | $10,000 | $180,000 | GHS 2,340,000 |
| Deputy Project Manager | 1 | 18 | $7,500 | $135,000 | GHS 1,755,000 |
| Project Coordinator | 1 | 18 | $5,000 | $90,000 | GHS 1,170,000 |
| Project Administrator | 1 | 18 | $3,500 | $63,000 | GHS 819,000 |
| Financial Manager / Controller | 1 | 18 | $6,500 | $117,000 | GHS 1,521,000 |
| Sub-Total: F. Project Management Office (Full 18 Months) | $585,000 | GHS 7,605,000 |

G. Compliance & Legal

| Role / Position | # | Mths | Rate / Month (USD) | Total (USD) | Total (GHS) |
| --- | --- | --- | --- | --- | --- |
| Compliance Officer — Data Protection (Act 843) | 1 | 12 | $7,000 | $84,000 | GHS 1,092,000 |
| AML/CFT Compliance Specialist | 1 | 8 | $8,000 | $64,000 | GHS 832,000 |
| Legal Advisor (Contract / IP / Regulatory) | 1 | 6 | $8,500 | $51,000 | GHS 663,000 |
| Sub-Total: G. Compliance & Legal | $199,000 | GHS 2,587,000 |

H. Stabilisation & Support Team (Months 7–18)

| Role / Position | # | Mths | Rate / Month (USD) | Total (USD) | Total (GHS) |
| --- | --- | --- | --- | --- | --- |
| Technical Support Engineer (L2/L3) | 3 | 12 | $6,000 | $216,000 | GHS 2,808,000 |
| System Administrator | 2 | 12 | $5,500 | $132,000 | GHS 1,716,000 |
| Help Desk / L1 Support Agent | 4 | 12 | $3,000 | $144,000 | GHS 1,872,000 |
| Blockchain Node Operator | 1 | 12 | $6,000 | $72,000 | GHS 936,000 |
| Sub-Total: H. Stabilisation & Support Team (Months 7–18) | $564,000 | GHS 7,332,000 |

I. Statutory Employment On-Costs (Ghana)

| On-Cost Item | Amount (USD) |
| --- | --- |
| SSNIT — Employer Contribution (13% of basic salary) | $245,000 |
| Tier 2 Pension Contribution (5% of basic salary) | $94,000 |
| Staff Medical Insurance (~USD 200/person/month, ~50 staff) | $108,000 |
| Professional Indemnity & Project Insurance | $65,000 |
| Staff Welfare & Team Activities | $28,000 |

| TOTAL PERSONNEL & HR COSTS | USD 3,250,000 |
| --- | --- |

# PAYMENT MILESTONE SCHEDULE

Payments are structured on a milestone basis, releasing tranches upon formal written sign-off by GoldBod for each deliverable. The structure is designed to align the vendor's cash flow with demonstrable project progress while protecting GoldBod's interests. A 2% performance retention is held until 12 months post-warranty expiry.

| Ref | Milestone Description | % | Amount (USD) | Amount (GHS) | Target Date |
| --- | --- | --- | --- | --- | --- |
| M0 | Contract Signing Advance | 15% | USD 1,698,750 | GHS 22,083,750 | Week 0 |
| M1 | Phase 1 Complete — Design, Architecture & Requirements | 12% | USD 1,359,000 | GHS 17,667,000 | Month 2 |
| M2 | Phase 2 Complete — Core Platform & Blockchain Development | 20% | USD 2,265,000 | GHS 29,445,000 | Month 4 |
| M3 | Phase 3 Complete — Integration & Testing | 10% | USD 1,132,500 | GHS 14,722,500 | Month 5 |
| M4 | Phase 4 Complete — Pilot Deployment | 8% | USD 906,000 | GHS 11,778,000 | Month 6 |
| M5 | Phase 5 — National Go-Live | 15% | USD 1,698,750 | GHS 22,083,750 | Month 6 |
| M6a | Stabilisation Q1 (2% × 3 months) | 6% | USD 679,500 | GHS 8,833,500 | Months 7–9 |
| M6b | Stabilisation Q2 (2% × 3 months) | 6% | USD 679,500 | GHS 8,833,500 | Months 10–12 |
| M6c | Stabilisation Q3 (1% × 3 months) | 3% | USD 339,750 | GHS 4,416,750 | Months 13–15 |
| M7 | Final Handover & Knowledge Transfer | 3% | USD 339,750 | GHS 4,416,750 | Month 18 |
| RET | Performance Retention (released post-warranty) | 2% | USD 226,500 | GHS 2,944,500 | Month 24 |
| TOTAL | Total Contract Value | 100% | USD 11,325,000 | GHS 147,225,000 | — |

Note: GoldBod is required to settle invoices within 30 days of milestone sign-off. Late payment will attract interest at the prevailing Bank of Ghana policy rate plus 2% per annum.

# CONTINGENCY BUDGET

A contingency provision is applied per cost category, calibrated to the complexity and risk profile of each workstream. Higher rates are applied to software development (12%) and systems integration (15%) to reflect scope uncertainty; lower rates apply to more predictable categories such as documentation (5%). An additional currency and tax risk reserve of USD 250,000 is included to cover GHS exchange rate movements exceeding 5% or unanticipated tax policy changes.

| # | Cost Category | Direct Cost (USD) | Rate | Contingency (USD) | Contingency (GHS) |
| --- | --- | --- | --- | --- | --- |
| 1 | Personnel & HR Costs | $3,250,000 | 8.0% | $260,000 | GHS 3,380,000 |
| 2 | Software Development | $1,980,000 | 12.0% | $237,600 | GHS 3,088,800 |
| 3 | Blockchain Infrastructure | $820,000 | 12.0% | $98,400 | GHS 1,279,200 |
| 4 | Cloud & Hosting (18 months) | $540,000 | 8.0% | $43,200 | GHS 561,600 |
| 5 | Software Licences & Tools | $310,000 | 5.0% | $15,500 | GHS 169,000 |
| 6 | Hardware & Field Equipment | $680,000 | 10.0% | $68,000 | GHS 884,000 |
| 7 | Deployment Costs | $400,000 | 10.0% | $40,000 | GHS 520,000 |
| 8 | Systems Integration (6 Agencies) | $640,000 | 15.0% | $96,000 | GHS 1,248,000 |
| 9 | Testing & Quality Assurance | $290,000 | 10.0% | $29,000 | GHS 377,000 |
| 10 | Training & Capacity Building | $420,000 | 10.0% | $42,000 | GHS 546,000 |
| 11 | Compliance & Regulatory | $180,000 | 8.0% | $14,400 | GHS 187,200 |
| 12 | Project Management & PMO | $380,000 | 8.0% | $30,400 | GHS 395,200 |
| 13 | Documentation & Deliverables | $95,000 | 5.0% | $4,750 | GHS 61,750 |
| 14 | Additional Risk Reserve (Currency / Tax) | $250,000 | Lump sum | $250,000 | GHS 3,250,000 |
|  | TOTAL CONTINGENCY |  |  | USD 1,229,250 | GHS 15,980,250 |

## Contingency Release Policy

- All contingency draws require a formal Contingency Release Request (CRR) with documented justification.

- Draws of USD 10,000 or less may be approved by the Project Manager.

- Draws exceeding USD 10,000 require Steering Committee approval.

- A contingency utilisation report is submitted with each monthly progress report to GoldBod.

- Any unspent contingency at project close is returned in full to GoldBod and is not retained by the vendor.

# GRAND TOTAL

| Budget Line | USD Amount | GHS Equivalent |
| --- | --- | --- |
| Direct Project Costs (Categories 1–15) | $10,750,000 | GHS 139,750,000 |
| Contingency Provision (10% blended, Category 16) | $575,000 | GHS 7,475,000 |
| TOTAL PROJECT BUDGET | $11,325,000 | GHS 147,225,000 |

Note: All GHS amounts are calculated at the indicative rate of 1 USD = 13 GHS (April 2026). The exchange rate will be locked at the date of contract signing. The contingency figure of USD 575,000 represents the approved 10% buffer against the total direct cost base (net of the additional currency/tax reserve of USD 250,000, which is included within the detailed contingency schedule at Section 15 of the accompanying budget workbook).

This budget is prepared in accordance with the Public Procurement Act, 2003 (Act 663, as amended) and is submitted in support of the Expression of Interest for the procurement of technical services for the Design, Development, Implementation, and Support of the Ghana Gold Board Traceability and Assurance System.