## 0. Assumptions
GHANA GOLD BOARD (GOLDBOD)
TRACEABILITY & ASSURANCE SYSTEM (TAS)
PROJECT BUDGET — KEY ASSUMPTIONS
REF: GR/GGB/TS/NCT/042/2026 ¦ April 2026
CORE FINANCIAL ASSUMPTIONS |  |  | BUDGET ALLOCATION BY CATEGORY
Assumption | Value | Notes | Category | Weight % | Allocated USD
Estimated Budget (USD) | 11355000 | ★ Change this to update the budget across all sheets | 1. Personnel & HR Costs | 28.7% | 3258609.2715
USD → GHS Exchange Rate | 13 | ★ Change this — GHS amounts recalculate automatically | 2. Software Development | 17.48% | 1985245.0331
Budget Date | April 2026 | Date of budget preparation | 3. Blockchain Infrastructure | 7.241% | 822172.1854
Contract Duration | 18 Months | 6 Mths Implementation + 12 Mths Stabilisation | 4. Cloud & Hosting (18 months) | 4.768% | 541430.4636
Procurement Method | QCBS | Quality & Cost Based Selection | 5. Software Licenses & Tools | 2.737% | 310821.1921
Primary Currency | USD | GHS equivalent calculated from rate above | 6. Hardware & Field Equipment | 6.004% | 681801.3245
Contingency Rate | 10% | Applied per category; PMO approval to release | 7. Systems Integration (6 agencies) | 5.651% | 641695.3642
FX Variance Buffer | ±5% | Built into contingency for exchange rate movements | 8. Testing & Quality Assurance | 2.561% | 290768.2119
Project Start Date | May 2026 | Indicative — subject to contract signing | 9. Training & Capacity Building | 3.709% | 421112.5828
|  |  | 10. Compliance & Legal | 1.589% | 180476.8212
GENERAL PROJECT ASSUMPTIONS |  |  | 11. Project Management & PMO | 3.355% | 381006.6225
1. All costs are in USD unless stated otherwise. GHS equivalent rates are indicative only. |  |  | 12. Pilot Programme | 1.545% | 175463.5762
2. Exchange rate locked at contract signing. FX fluctuations covered by 5% contingency buffer. |  |  | 13. National Deployment | 2.119% | 240635.7616
3. Personnel rates are blended for onshore/offshore delivery mix. |  |  | 14. Stabilisation & Support (12 mths) | 6.623% | 751986.755
4. Software licence costs assume 18-month project duration with annual renewal option. |  |  | 15. Documentation & Deliverables | 0.8389% | 95251.6556
5. Hardware procurement subject to GoldBod import duty and procurement regulations. |  |  | 16. Contingency (10%) | 5.077% | 576523.1788
6. Contingency (10%) requires written PMO approval for release; unspent amounts returned to GoldBod. |  |  | TOTAL | 100% | 11355000
7. All milestones subject to formal sign-off before subsequent tranche is released.
8. Training costs assume train-the-trainer model for national rollout efficiency.
Colour Legend: Blue text = User input ¦ Black text = Formula ¦ Yellow background = Key assumption to review ¦ Green text = Cross-sheet link

## Budget-Summary
GHANA GOLD BOARD (GOLDBOD)
TRACEABILITY & ASSURANCE SYSTEM (TAS)
PROJECT BUDGET SUMMARY
REF: GR/GGB/TS/NCT/042/2026 ¦ April 2026
Estimated Budget: | 11355000 |  | Exchange Rate: | 13 | GHS/USD
# | Cost Category | Description | USD Amount | GHS Equivalent | % of Total
1 | 1. Personnel & HR Costs | Core team: developers, architects, QA, PMs, compliance officers, support staff. Includes statutory oncosts (SSNIT, Tier 2, medical). | 3258609.2715 | 42361920.5298 | 28.7%
2 | 2. Software Development | Full-stack blockchain platform: smart contracts, APIs, mobile apps, web dashboards, admin portal. | 1985245.0331 | 25808185.4305 | 17.48%
3 | 3. Blockchain Infrastructure | Hyperledger Fabric nodes, consensus infrastructure, HSMs, certificate authority setup. | 822172.1854 | 10688238.4106 | 7.241%
4 | 4. Cloud & Hosting (18 months) | AWS/Azure hosting, CDN, DR environment, monitoring & backup services for 18 months. | 541430.4636 | 7038596.0265 | 4.768%
5 | 5. Software Licenses & Tools | Development tools, CI/CD pipelines, security scanners, design & collaboration platforms. | 310821.1921 | 4040675.4967 | 2.737%
6 | 6. Hardware & Field Equipment | Tablets, GPS devices, digital scales, biometric scanners, ruggedised field kits for regional offices. | 681801.3245 | 8863417.2185 | 6.004%
7 | 7. Systems Integration (6 agencies) | API integration with 6 government agencies: GRA, PMMC, Minerals Commission, NIA, FIC, Bank of Ghana. | 641695.3642 | 8342039.7351 | 5.651%
8 | 8. Testing & Quality Assurance | Functional, regression, load, security (penetration) testing and UAT coordination. | 290768.2119 | 3779986.755 | 2.561%
9 | 9. Training & Capacity Building | Train-the-trainer programme, e-learning platform, regional workshops, user manuals & change management. | 421112.5828 | 5474463.5762 | 3.709%
10 | 10. Compliance & Legal | Data protection (Act 843), AML/CFT compliance, legal advisory, regulatory submissions. | 180476.8212 | 2346198.6755 | 1.589%
11 | 11. Project Management & PMO | PMO office, project & financial management, governance, reporting, steering committee support. | 381006.6225 | 4953086.0927 | 3.355%
12 | 12. Pilot Programme | Pilot deployment in 2 selected regions with controlled rollout and feedback loop. | 175463.5762 | 2281026.4901 | 1.545%
13 | 13. National Deployment | Phased national rollout to all 16 regions with logistics, connectivity and on-site commissioning. | 240635.7616 | 3128264.9007 | 2.119%
14 | 14. Stabilisation & Support (12 mths) | L1–L3 support, system administration, SLA monitoring, bug fixes and optimisation for 12 months post go-live. | 751986.755 | 9775827.8146 | 6.623%
15 | 15. Documentation & Deliverables | Technical documentation, user guides, SOPs, handover packs, knowledge transfer deliverables. | 95251.6556 | 1238271.5232 | 0.8389%
16 | 16. Contingency (10%) | 10% contingency on direct costs. Released only with written PMO approval. Unspent funds returned. | 576523.1788 | 7494801.3245 | 5.077%
| TOTAL PROJECT BUDGET |  | 11355000 | 147615000 | 100%
Notes:
1. All amounts in USD. GHS equivalents are indicative at the exchange rate shown above.
2. Budget allocations are proportional — changing the Estimated Budget automatically recalculates all line items.
3. Contingency (10%) requires written PMO approval for release. Unspent amounts returned to GoldBod.
4. Exchange rate locked at contract signing. ±5% FX variance buffer built into contingency.
5. Contract duration: 18 months (6 months implementation + 12 months stabilisation & support).
Prepared: April 2026 ¦ Procurement Method: QCBS (Quality & Cost Based Selection)

## Cover
GHANA GOLD BOARD (GOLDBOD) TRACEABILITY & ASSURANCE SYSTEM (TAS) PROJECT BUDGET — REF: GR/GGB/TS/NCT/042/2026
| Contract Duration: | 18 Months (6 Mths Implementation + 12 Mths Stabilisation)
| Procurement Method: | Quality & Cost Based Selection (QCBS)
| Currency (Primary): | USD (with GHS equivalent at 13.00 USD/GHS)
| Exchange Rate: | 1 USD = 13.00 GHS (Indicative – April 2026)
| Budget Date: | April 2026
| Regulatory Framework: | Public Procurement Act, 2003 (Act 663 as amended)
EXECUTIVE BUDGET SUMMARY
| Cost Category | USD Amount | GHS Amount | % of Total
| 1. Personnel & HR Costs | 3258609.2715 | 42361920.5298 | 28.7%
| 2. Software Development | 1985245.0331 | 25808185.4305 | 17.48%
| 3. Blockchain Infrastructure | 822172.1854 | 10688238.4106 | 7.241%
| 4. Cloud & Hosting (18 months) | 541430.4636 | 7038596.0265 | 4.768%
| 5. Software Licenses & Tools | 310821.1921 | 4040675.4967 | 2.737%
| 6. Hardware & Field Equipment | 681801.3245 | 8863417.2185 | 6.004%
| 7. Systems Integration (6 agencies) | 641695.3642 | 8342039.7351 | 5.651%
| 8. Testing & Quality Assurance | 290768.2119 | 3779986.755 | 2.561%
| 9. Training & Capacity Building | 421112.5828 | 5474463.5762 | 3.709%
| 10. Compliance & Legal | 180476.8212 | 2346198.6755 | 1.589%
| 11. Project Management & PMO | 381006.6225 | 4953086.0927 | 3.355%
| 12. Pilot Programme | 175463.5762 | 2281026.4901 | 1.545%
| 13. National Deployment | 240635.7616 | 3128264.9007 | 2.119%
| 14. Stabilisation & Support (12 mths) | 751986.755 | 9775827.8146 | 6.623%
| 15. Documentation & Deliverables | 95251.6556 | 1238271.5232 | 0.8389%
| 16. Contingency (10%) | 576523.1788 | 7494801.3245 | 5.077%
| TOTAL PROJECT BUDGET | 11355000 | 147615000 | 100.0%

## 1. Personnel Costs
SECTION 1 — PERSONNEL & HR COSTS
| Role / Position | Monthly Rate (USD) | # Staff | Months | Total USD | Total GHS
A. TECHNICAL DEVELOPMENT TEAM (Implementation Phase)
| Blockchain Architect / Lead Developer | 12000 | 1 | 8 | 96000 | 1248000
| Senior Backend Developer (Blockchain) | 9000 | 2 | 6 | 108000 | 1404000
| Senior Backend Developer (API/Core) | 8500 | 2 | 6 | 102000 | 1326000
| Frontend Developer (Web Portal) | 7000 | 2 | 6 | 84000 | 1092000
| Mobile App Developer (Android/iOS) | 7500 | 2 | 6 | 90000 | 1170000
| Smart Contract Developer | 9500 | 1 | 5 | 47500 | 617500
| DevOps / Cloud Engineer | 8000 | 2 | 7 | 112000 | 1456000
| Database Administrator | 7000 | 1 | 6 | 42000 | 546000
| Cybersecurity / Security Engineer | 8500 | 1 | 6 | 51000 | 663000
| Sub-Total: A. TECHNICAL DEVELOPMENT TEAM (Implementation Phase) |  |  |  | 732500 | 9522500
B. QA & TESTING TEAM
| QA Lead / Test Manager | 7500 | 1 | 5 | 37500 | 487500
| QA Engineer / Functional Tester | 5500 | 3 | 5 | 82500 | 1072500
| Test Automation Engineer | 6500 | 1 | 4 | 26000 | 338000
| Penetration Tester / Security Auditor | 8000 | 1 | 2 | 16000 | 208000
| Sub-Total: B. QA & TESTING TEAM |  |  |  | 162000 | 2106000
C. UI/UX & BUSINESS ANALYSIS
| Lead UI/UX Designer | 7000 | 1 | 5 | 35000 | 455000
| Junior UI/UX Designer | 4500 | 1 | 4 | 18000 | 234000
| Business Analyst (Gold Supply Chain) | 7000 | 2 | 6 | 84000 | 1092000
| Requirements Engineer | 6000 | 1 | 4 | 24000 | 312000
| Domain Expert – AML/CFT Compliance | 9000 | 1 | 4 | 36000 | 468000
| Sub-Total: C. UI/UX & BUSINESS ANALYSIS |  |  |  | 197000 | 2561000
D. INTEGRATION & DATA SPECIALISTS
| Integration Architect | 9000 | 1 | 5 | 45000 | 585000
| API Developer / Integration Engineer | 7000 | 2 | 5 | 70000 | 910000
| Data Engineer | 7000 | 1 | 6 | 42000 | 546000
| Data Scientist / Analytics Specialist | 7500 | 1 | 4 | 30000 | 390000
| Sub-Total: D. INTEGRATION & DATA SPECIALISTS |  |  |  | 187000 | 2431000
E. TRAINING & CHANGE MANAGEMENT
| Training Programme Manager | 6500 | 1 | 6 | 39000 | 507000
| Field Training Specialist (Regional) | 4500 | 4 | 4 | 72000 | 936000
| Change Management Consultant | 8000 | 1 | 4 | 32000 | 416000
| Technical Writer / Documentation Spec. | 5000 | 1 | 6 | 30000 | 390000
| E-Learning / LMS Developer | 5500 | 1 | 3 | 16500 | 214500
| Sub-Total: E. TRAINING & CHANGE MANAGEMENT |  |  |  | 189500 | 2463500
F. PROJECT MANAGEMENT
| Project Manager | 10000 | 1 | 18 | 180000 | 2340000
| Deputy Project Manager | 7500 | 1 | 18 | 135000 | 1755000
| Project Coordinator | 5000 | 1 | 18 | 90000 | 1170000
| Project Administrator | 3500 | 1 | 18 | 63000 | 819000
| Financial Manager / Controller | 6500 | 1 | 18 | 117000 | 1521000
| Sub-Total: F. PROJECT MANAGEMENT |  |  |  | 585000 | 7605000
G. COMPLIANCE & LEGAL
| Compliance Officer – Data Protection (Act 843) | 7000 | 1 | 12 | 84000 | 1092000
| AML/CFT Compliance Specialist | 8000 | 1 | 8 | 64000 | 832000
| Legal Advisor (Contract / IP / Regulatory) | 8500 | 1 | 6 | 51000 | 663000
| Sub-Total: G. COMPLIANCE & LEGAL |  |  |  | 199000 | 2587000
H. STABILISATION & SUPPORT TEAM (Months 7–18)
| Technical Support Engineer (L2/L3) | 6000 | 3 | 12 | 216000 | 2808000
| System Administrator | 5500 | 2 | 12 | 132000 | 1716000
| Help Desk / L1 Support Agent | 3000 | 4 | 12 | 144000 | 1872000
| Blockchain Node Operator | 6000 | 1 | 12 | 72000 | 936000
| Sub-Total: H. STABILISATION & SUPPORT TEAM (Months 7–18) |  |  |  | 564000 | 7332000
I. GHANA EMPLOYMENT ONCOSTS (Statutory)
| SSNIT – Employer Contribution (13% of basic salary) |  |  |  | 245000 | 3185000
| Tier 2 Pension Contribution (5% of basic salary) |  |  |  | 94000 | 1222000
| Staff Medical Insurance Allowance (est. $200/person/month, ~50 staff) |  |  |  | 108000 | 1404000
| Professional Indemnity & Project Insurance |  |  |  | 65000 | 845000
| Staff Welfare & Team Activities |  |  |  | 28000 | 364000
| TOTAL PERSONNEL & HR COSTS |  |  |  | 3356000 | 43628000
NOTE: Blue text = hardcoded inputs (rates, headcount, duration). Black text = formulas. Green text = GHS conversions at 1 USD = 13.00 GHS (indicative).

## 2. Software Development
SECTION 2 — SOFTWARE DEVELOPMENT & PROJECT IMPLEMENTATION
| Development Activity / Deliverable | Estimated Cost (USD) | Estimated Cost (GHS)
PHASE 1: DESIGN & REQUIREMENTS (Months 1–2)
| System Architecture Design & Technical Blueprint | 85000 | 1105000
| Blockchain Network Architecture Specification | 55000 | 715000
| UX Research & Wireframing (all user roles) | 45000 | 585000
| Stakeholder Workshops & Requirements Workshops (3 rounds) | 30000 | 390000
| Data Model & Database Schema Design | 25000 | 325000
| Security Architecture & Threat Modelling | 35000 | 455000
| Integration Architecture & API Design (6 agencies) | 40000 | 520000
| Sub-Total: PHASE 1: DESIGN & REQUIREMENTS (Months 1–2) | 315000 | 4095000
PHASE 2: CORE PLATFORM DEVELOPMENT (Months 2–4)
| Blockchain Network Setup – Hyperledger Fabric (permissioned) | 120000 | 1560000
| Smart Contract Development & Auditing | 95000 | 1235000
| Core Backend API Development (Node.js / Python) | 150000 | 1950000
| Supply Chain Transaction Module | 80000 | 1040000
| KYC/AML Module (identity & compliance) | 70000 | 910000
| Assay & Weight Recording Module | 55000 | 715000
| Chain-of-Custody / Provenance Ledger Module | 85000 | 1105000
| Admin Dashboard & Analytics Portal (Web) | 75000 | 975000
| Reporting & BI Module (OECD/LBMA/FIC reports) | 60000 | 780000
| Notification Engine (SMS, email, push) | 30000 | 390000
| Document Management & IPFS Off-chain Storage | 40000 | 520000
| Role-Based Access Control & Permissioning Engine | 35000 | 455000
| Sub-Total: PHASE 2: CORE PLATFORM DEVELOPMENT (Months 2–4) | 895000 | 11635000
PHASE 3: MOBILE APPLICATION DEVELOPMENT
| Android Mobile App – Field Officers & Miners | 80000 | 1040000
| iOS Mobile App – Field Officers | 65000 | 845000
| Offline Mode & Data Sync Engine | 45000 | 585000
| QR/NFC/RFID Scanner Integration | 25000 | 325000
| GPS & Geolocation Integration | 20000 | 260000
| Digital Signature / e-Certificate Module | 30000 | 390000
| Photo Capture & Evidence Upload Module | 20000 | 260000
| Sub-Total: PHASE 3: MOBILE APPLICATION DEVELOPMENT | 285000 | 3705000
PHASE 4: DEVOPS, CI/CD & INFRASTRUCTURE-AS-CODE
| CI/CD Pipeline Setup (GitHub Actions / Jenkins) | 25000 | 325000
| Docker / Kubernetes Container Orchestration | 35000 | 455000
| Infrastructure-as-Code (Terraform / Ansible) | 20000 | 260000
| Environment Setup: Dev / Staging / UAT / Production | 30000 | 390000
| Automated Deployment & Rollback Procedures | 15000 | 195000
| Performance Monitoring & Alerting Setup | 18000 | 234000
| Sub-Total: PHASE 4: DEVOPS, CI/CD & INFRASTRUCTURE-AS-CODE | 143000 | 1859000
PHASE 5: PILOT DEVELOPMENT (Months 5–6)
| Pilot Configuration for 2–3 Mine Sites | 40000 | 520000
| Pilot-Specific Customisation & Field Adaptation | 25000 | 325000
| Iterative Bug Fixes & Field Feedback Integration | 30000 | 390000
| Load & Stress Testing for Pilot Volume | 18000 | 234000
| Sub-Total: PHASE 5: PILOT DEVELOPMENT (Months 5–6) | 113000 | 1469000
PHASE 6: NATIONAL DEPLOYMENT & GO-LIVE
| National Rollout Configuration & Data Migration | 45000 | 585000
| Go-Live Support (War Room, 24/7 for 2 weeks) | 22000 | 286000
| Post Go-Live Hotfix Sprint (first 4 weeks) | 25000 | 325000
| Sub-Total: PHASE 6: NATIONAL DEPLOYMENT & GO-LIVE | 92000 | 1196000
ONGOING DEVELOPMENT – STABILISATION (Months 7–18)
| Quarterly Feature Enhancements (4 sprints × 3 months) | 80000 | 1040000
| Bug Fix & Patch Management | 40000 | 520000
| Performance Tuning & Optimisation | 25000 | 325000
| Regulatory & Compliance Updates | 20000 | 260000
| API Version Upgrades (agency systems) | 15000 | 195000
| Sub-Total: ONGOING DEVELOPMENT – STABILISATION (Months 7–18) | 180000 | 2340000
| TOTAL SOFTWARE DEVELOPMENT | 2023000 | 26299000

## 3. Infrastructure & Licenses
SECTION 3 — BLOCKCHAIN INFRASTRUCTURE, CLOUD & SOFTWARE LICENSES
| Item | Unit Cost (USD) | Qty / Months | Total USD | Total GHS
BLOCKCHAIN INFRASTRUCTURE
| Hyperledger Fabric Platform Support & SLA | 15000 | 18 | 270000 | 3510000
| Blockchain Node Hosting (6 validator nodes × cloud) | 1800 | 18 | 32400 | 421200
| Hardware Security Modules (HSM) – cloud-based KMS | 4000 | 18 | 72000 | 936000
| Blockchain Explorer & Monitoring Tool | 1200 | 18 | 21600 | 280800
| Smart Contract Audit (external firm) | 25000 | 1 | 25000 | 325000
| Certificate Authority Setup & Annual Maintenance | 8000 | 1 | 8000 | 104000
| IPFS / Off-Chain Distributed Storage | 1000 | 18 | 18000 | 234000
| Blockchain Disaster Recovery Node | 1500 | 18 | 27000 | 351000
| Sub-Total: BLOCKCHAIN INFRASTRUCTURE |  |  | 474000 | 6162000
CLOUD & HOSTING INFRASTRUCTURE (18 months)
| Compute – Application Servers (prod + staging + dev) | 3500 | 18 | 63000 | 819000
| Database Servers (managed PostgreSQL + Redis) | 1800 | 18 | 32400 | 421200
| Object Storage (S3 equivalent – docs, images, logs) | 600 | 18 | 10800 | 140400
| CDN – Content Delivery Network (Ghana region) | 400 | 18 | 7200 | 93600
| Load Balancer & Auto-Scaling | 350 | 18 | 6300 | 81900
| VPN & Networking / Egress Costs | 500 | 18 | 9000 | 117000
| Web Application Firewall (WAF) + DDoS Protection | 800 | 18 | 14400 | 187200
| SSL Certificates & PKI | 200 | 18 | 3600 | 46800
| SIEM / Security Monitoring (cloud) | 900 | 18 | 16200 | 210600
| Backup & Disaster Recovery (cross-region replication) | 1200 | 18 | 21600 | 280800
| Data Residency / Local DC Co-location (Act 843) | 2500 | 18 | 45000 | 585000
| Sub-Total: CLOUD & HOSTING INFRASTRUCTURE (18 months) |  |  | 229500 | 2983500
SOFTWARE LICENSES & DEVELOPMENT TOOLS
| GitHub Enterprise (version control & CI/CD) | 3000 | 1 | 3000 | 39000
| Jira + Confluence (project management & docs) | 2500 | 1 | 2500 | 32500
| Figma Organisation (UI/UX design) | 1200 | 1 | 1200 | 15600
| SonarQube (code quality) | 1500 | 1 | 1500 | 19500
| Postman Enterprise (API testing) | 1000 | 1 | 1000 | 13000
| Datadog APM (application monitoring) | 4800 | 1 | 4800 | 62400
| PagerDuty (incident management) | 1200 | 1 | 1200 | 15600
| Power BI Premium (analytics & dashboards) | 4200 | 1 | 4200 | 54600
| LoadRunner / JMeter Pro (performance testing) | 2500 | 1 | 2500 | 32500
| Burp Suite Pro (security testing) | 1500 | 1 | 1500 | 19500
| Microsoft 365 (team productivity – 30 users) | 5400 | 1 | 5400 | 70200
| Sub-Total: SOFTWARE LICENSES & DEVELOPMENT TOOLS |  |  | 28800 | 374400
THIRD-PARTY API & COMPLIANCE SERVICES (18 months)
| Ghana Card / NIA Identity Verification API | 1500 | 18 | 27000 | 351000
| AML/CFT Sanctions Screening (Refinitiv/LexisNexis) | 2000 | 18 | 36000 | 468000
| PEP & Adverse Media Screening Service | 1200 | 18 | 21600 | 280800
| SMS Gateway – Bulk SMS (MTN/Vodafone Ghana) | 800 | 18 | 14400 | 187200
| Google Maps / Geolocation API | 500 | 18 | 9000 | 117000
| Email Delivery Service (SendGrid / AWS SES) | 200 | 18 | 3600 | 46800
| DocuSign / Digital Signature Service | 600 | 18 | 10800 | 140400
| Source Code Escrow Agreement | 3000 | 1 | 3000 | 39000
| Sub-Total: THIRD-PARTY API & COMPLIANCE SERVICES (18 months) |  |  | 125400 | 1630200
| TOTAL INFRASTRUCTURE & LICENSES |  |  | 857700 | 11150100

## 4. Hardware & Other Costs
SECTION 4 — HARDWARE, TRAINING, INTEGRATION, COMPLIANCE & PROJECT MANAGEMENT
| Item / Activity | Unit Cost (USD) | Quantity | Total USD | Total GHS
HARDWARE & FIELD EQUIPMENT
| Rugged Android Smartphones for Field Officers | 350 | 120 | 42000 | 546000
| Protective Cases & Screen Protectors | 30 | 120 | 3600 | 46800
| QR Code / NFC Scanners (handheld) | 280 | 80 | 22400 | 291200
| Barcode Label Printer (for serialised tags) | 450 | 20 | 9000 | 117000
| Label Printing Supplies (rolls, ink – 18 months) | 600 | 1 | 600 | 7800
| Digital Scales with Data Capture (assay sites) | 1200 | 30 | 36000 | 468000
| Field GPS Handheld Units (remote areas) | 200 | 30 | 6000 | 78000
| Mobile Hotspot / MiFi Devices (LTE) | 150 | 50 | 7500 | 97500
| Solar Chargers & Power Banks (off-grid) | 80 | 80 | 6400 | 83200
| Laptop Computers (project team) | 1200 | 25 | 30000 | 390000
| Desktop Workstations (GoldBod offices) | 1000 | 20 | 20000 | 260000
| Network Switches & WiFi Access Points | 350 | 15 | 5250 | 68250
| UPS Units (data centre / server room) | 800 | 10 | 8000 | 104000
| Server Rack & Cooling (on-premise components) | 5000 | 2 | 10000 | 130000
| Document Scanner (A3, office) | 800 | 5 | 4000 | 52000
| Equipment Insurance (18 months, all hardware) | 8000 | 1 | 8000 | 104000
| Sub-Total: HARDWARE & FIELD EQUIPMENT |  |  | 218750 | 2843750
SYSTEMS INTEGRATION — 6 GOVERNMENT AGENCIES
| Minerals Commission – Licensing & Cadastre API | 45000 | 1 | 45000 | 585000
| Ghana Revenue Authority (GRA) – Customs Export API | 40000 | 1 | 40000 | 520000
| Bank of Ghana – Payment & FX Reporting API | 45000 | 1 | 45000 | 585000
| Financial Intelligence Centre (FIC) – STR/SAR Filing | 38000 | 1 | 38000 | 494000
| Environmental Protection Authority (EPA) | 32000 | 1 | 32000 | 416000
| Water Resources Commission (WRC) | 28000 | 1 | 28000 | 364000
| Integration Testing & End-to-End Validation | 35000 | 1 | 35000 | 455000
| API Gateway Setup & Developer Portal | 20000 | 1 | 20000 | 260000
| Ongoing Integration Maintenance (12 months) | 25000 | 1 | 25000 | 325000
| Sub-Total: SYSTEMS INTEGRATION — 6 GOVERNMENT AGENCIES |  |  | 308000 | 4004000
TRAINING & CAPACITY BUILDING
| Training Needs Assessment & Curriculum Development | 15000 | 1 | 15000 | 195000
| LMS Setup & E-Learning Module Production | 22000 | 1 | 22000 | 286000
| User Manuals, Video Guides & Visual Aids | 12000 | 1 | 12000 | 156000
| GoldBod IT Staff – Blockchain & System Admin Training | 8000 | 1 | 8000 | 104000
| Field Officer Training (10 regions × 2 batches) | 4500 | 20 | 90000 | 1170000
| Tier 1/2 Buyer & Kitchen Operator Training | 3000 | 30 | 90000 | 1170000
| Aggregator & Transporter Training | 2500 | 20 | 50000 | 650000
| Miner / Small-Scale ASM Sensitisation Workshops | 1800 | 40 | 72000 | 936000
| Train-the-Trainer Programme | 10000 | 1 | 10000 | 130000
| Training Venue, Catering & Logistics (regional) | 1200 | 20 | 24000 | 312000
| Refresher Training – Stabilisation Phase | 25000 | 1 | 25000 | 325000
| Change Management Programme | 18000 | 1 | 18000 | 234000
| Sub-Total: TRAINING & CAPACITY BUILDING |  |  | 436000 | 5668000
TESTING & QUALITY ASSURANCE
| Test Environment Hosting (UAT + staging – 6 months) | 5000 | 6 | 30000 | 390000
| Automated Testing Framework Setup | 18000 | 1 | 18000 | 234000
| Performance / Load Testing (JMeter) | 12000 | 1 | 12000 | 156000
| External Security Audit & Penetration Testing | 35000 | 1 | 35000 | 455000
| Blockchain Security Audit (specialist firm) | 25000 | 1 | 25000 | 325000
| LBMA / OECD Compliance Assessment | 20000 | 1 | 20000 | 260000
| ISO 27001 Gap Analysis & Preparation | 18000 | 1 | 18000 | 234000
| UAT Facilitation (multi-site, all stakeholders) | 15000 | 1 | 15000 | 195000
| Usability / Field Testing (remote sites) | 8000 | 1 | 8000 | 104000
| Test Defect Tracking Tool License (1 year) | 2000 | 1 | 2000 | 26000
| Sub-Total: TESTING & QUALITY ASSURANCE |  |  | 183000 | 2379000
COMPLIANCE, LEGAL & REGULATORY
| Data Protection Impact Assessment (DPIA – Act 843) | 12000 | 1 | 12000 | 156000
| Privacy Policy & Data Processing Agreements (legal) | 8000 | 1 | 8000 | 104000
| AML/CFT Policy Framework & Legal Review | 10000 | 1 | 10000 | 130000
| FATF / OECD Compliance Framework Documentation | 12000 | 1 | 12000 | 156000
| IP Assignment & Open-Source Licence Review | 6000 | 1 | 6000 | 78000
| SOC 2 Type II Audit Preparation | 20000 | 1 | 20000 | 260000
| Professional Indemnity Insurance (18 months) | 18000 | 1 | 18000 | 234000
| Cyber Liability Insurance (18 months) | 12000 | 1 | 12000 | 156000
| Legal Advisor – Contract Review & Disputes | 15000 | 1 | 15000 | 195000
| PPA Registration, Tax Clearance & Filings | 5000 | 1 | 5000 | 65000
| Withholding Tax Provision (est. on foreign services) | 20000 | 1 | 20000 | 260000
| VAT on Applicable Local Costs (15%) | 15000 | 1 | 15000 | 195000
| Sub-Total: COMPLIANCE, LEGAL & REGULATORY |  |  | 153000 | 1989000
PROJECT MANAGEMENT & GOVERNANCE (PMO)
| PMO Setup & Project Management Software | 8000 | 1 | 8000 | 104000
| Monthly Steering Committee Meetings (18 months) | 1200 | 18 | 21600 | 280800
| Project Launch Event & National Go-Live Ceremony | 20000 | 1 | 20000 | 260000
| International Airfare (expert missions, 4 visits) | 5000 | 4 | 20000 | 260000
| Accommodation & Per Diem (international experts) | 3500 | 4 | 14000 | 182000
| Domestic Travel – Regional Site Visits (18 months) | 12000 | 1 | 12000 | 156000
| Equipment Transportation & Logistics | 8000 | 1 | 8000 | 104000
| Office Rental & Running Costs (PMO office, 18 mths) | 2500 | 18 | 45000 | 585000
| Communication & Utilities (18 months) | 1000 | 18 | 18000 | 234000
| Monthly Progress Reports & Deliverable Production | 1500 | 18 | 27000 | 351000
| Public Relations & Media Engagement | 10000 | 1 | 10000 | 130000
| Sub-Total: PROJECT MANAGEMENT & GOVERNANCE (PMO) |  |  | 203600 | 2646800
PILOT PROGRAMME (Months 5–6)
| Pilot Site Setup & Configuration (3 sites) | 20000 | 3 | 60000 | 780000
| Pilot Equipment Deployment & Installation | 10000 | 1 | 10000 | 130000
| Pilot Monitoring, Evaluation & Reporting | 12000 | 1 | 12000 | 156000
| Pilot Training & On-Site Support | 8000 | 1 | 8000 | 104000
| Pilot Iteration & System Refinement | 18000 | 1 | 18000 | 234000
| Pilot Closure Report & Go/No-Go Assessment | 5000 | 1 | 5000 | 65000
| Sub-Total: PILOT PROGRAMME (Months 5–6) |  |  | 113000 | 1469000
NATIONAL DEPLOYMENT (Month 6)
| National Infrastructure Rollout – 10 Regions | 35000 | 1 | 35000 | 455000
| Regional Equipment Delivery & Installation | 20000 | 1 | 20000 | 260000
| Go-Live 24/7 War Room Support (2 weeks) | 15000 | 1 | 15000 | 195000
| Communications Campaign & Awareness | 12000 | 1 | 12000 | 156000
| National Deployment Documentation | 5000 | 1 | 5000 | 65000
| Sub-Total: NATIONAL DEPLOYMENT (Month 6) |  |  | 87000 | 1131000
DOCUMENTATION & KNOWLEDGE TRANSFER DELIVERABLES
| System Architecture & Technical Documentation | 10000 | 1 | 10000 | 130000
| User Manuals (all roles, multi-language) | 8000 | 1 | 8000 | 104000
| Administrator & IT Operations Manual | 6000 | 1 | 6000 | 78000
| API Developer Documentation & Swagger Specs | 5000 | 1 | 5000 | 65000
| Training Curricula & Certification Materials | 6000 | 1 | 6000 | 78000
| Handover Report & Sustainability Plan | 8000 | 1 | 8000 | 104000
| Source Code Handover & Repository Documentation | 5000 | 1 | 5000 | 65000
| Sub-Total: DOCUMENTATION & KNOWLEDGE TRANSFER DELIVERABLES |  |  | 48000 | 624000
| TOTAL – HARDWARE, TRAINING, INTEGRATION, COMPLIANCE & PMO |  |  | 1750350 | 22754550

## 5. Payment Milestones
PAYMENT MILESTONE SCHEDULE
| Milestone | Description | % of Total | Amount (USD) | Amount (GHS) | Expected Date
| M0 | Contract Signing Advance | 15% | 1703250 | 22142250 | Week 0
| M1 | Phase 1 Completion – Design, Architecture & Requirements | 12% | 1362600 | 17713800 | Month 2
| M2 | Phase 2 Completion – Core Platform & Blockchain Development | 20% | 2271000 | 29523000 | Month 4
| M3 | Phase 3 Completion – Integration & Testing | 10% | 1135500 | 14761500 | Month 5
| M4 | Phase 4 Completion – Pilot Deployment | 8% | 908400 | 11809200 | Month 6
| M5 | Phase 5 – National Go-Live | 15% | 1703250 | 22142250 | Month 6
| M6a | Stabilisation – Quarter 1 (Monthly 2% × 3) | 6% | 681300 | 8856900 | Months 7–9
| M6b | Stabilisation – Quarter 2 (Monthly 2% × 3) | 6% | 681300 | 8856900 | Months 10–12
| M6c | Stabilisation – Quarter 3 (Monthly 1% × 3) | 3% | 340650 | 4428450 | Months 13–15
| M7 | Final Handover & Knowledge Transfer | 3% | 340650 | 4428450 | Month 18
| RET | Performance Retention (released post-warranty) | 2% | 227100 | 2952300 | Month 24
| TOTAL CONTRACT VALUE |  | 100% | 11355000 | 147615000

## 6. Financial Risk Register
FINANCIAL RISK REGISTER
Risk ID | Risk Description | Probability | Impact | Cost Impact | Mitigation Strategy
FR-01 | Currency exchange rate fluctuation (GHS depreciation) | Medium | High | ±5–10% on GHS costs | Build 5% FX buffer; USD-denominated contracts
FR-02 | Scope creep & change requests | High | High | +10–20% on dev costs | Strict change control; change request pricing schedule
FR-03 | Delayed payments from GoldBod/GoG | Medium | Medium | Cash flow impact | Milestone-based invoicing; advance payment
FR-04 | Integration complexity underestimated | High | High | +15–25% on integration | Detailed API assessment; dedicated integration PM
FR-05 | Blockchain implementation complexity | Medium | High | +10–20% on blockchain | Expert consultation; PoC before full build
FR-06 | Training requirements underestimated | Medium | Medium | +10–15% on training | Phased training; early needs assessment
FR-07 | Equipment procurement delays (import) | Medium | Medium | Schedule impact | Early ordering; identify local alternatives
FR-08 | Import duty / tax increases | Low | Medium | +3–5% on hardware | Forward purchasing; monitor tax policy
FR-09 | Technology cost inflation (cloud/SaaS) | Medium | Medium | +5% on cloud costs | Reserved instances; multi-year licensing
FR-10 | Third-party API unavailability (Ghana Card, GRA) | Medium | High | Timeline impact | Early engagement; mock APIs for dev/test
FR-11 | Security breach during stabilisation | Low | Very High | Unbudgeted incident response | Cyber insurance; SIEM; penetration testing
FR-12 | Key personnel attrition (blockchain talent) | Medium | High | +5–10% on recruitment | Competitive rates; retention bonuses

## 7. Assumptions
KEY ASSUMPTIONS & CONSTRAINTS
| Assumption Category | Detail
| Exchange Rate | 1 USD = 13.00 GHS (indicative, April 2026). Rates locked at contract signing.
| Exchange Rate Variance | ±5% buffer built into contingency for FX movements.
| Ghana Inflation | ~20% p.a. local inflation assumed; escalation clause to be negotiated for GHS costs beyond Month 6.
| Cloud Cost Inflation | ±5% year-on-year; reserved instance pricing to be secured at contract start.
| Contract Start | Contract signature assumed Q2 2026; Phase 1 begins within 1 week of signing.
| Project Duration | 18 months – 6 months implementation + 12 months stabilisation & support.
| Tax – VAT | 15% VAT applies on all locally procured goods and services. Included in local cost estimates.
| Tax – WHT | Withholding tax on foreign service payments per Ghana Revenue Authority rates. Provision included.
| Tax – PAYE | Employer PAYE obligations for all Ghanaian staff. Managed via payroll.
| SSNIT | 13% employer SSNIT contribution on basic salary of all Ghanaian employees.
| Tier 2 Pension | 5% employer Tier 2 contribution on basic salary.
| Scope | No material scope changes assumed. Change requests priced separately per agreed schedule.
| Agency Integration | GoldBod will facilitate introductions and access to all 6 government agencies within Month 1.
| Ghana Card API | NIA Ghana Card identity verification API is available and accessible by contract start.
| Data Residency | Hybrid cloud approach assumed; primary data stored in Ghana-based data centre per Act 843.
| Field Coverage | MTN / Vodafone 4G coverage assumed at all operational sites; satellite fallback for remote areas.
| Hardware Import | Import duties on hardware est. 20% on CIF value; cleared via client's government waiver if available.
| Contingency | 10% contingency on all direct project costs. Contingency release requires written approval from GoldBod PMO.
| Local Content | Minimum 60% Ghanaian personnel by headcount; minimum 40% local sub-contracting spend committed.
| Public Procurement | All procurement sub-thresholds comply with Act 663 (as amended); prior approvals obtained.
| Payment Terms | Milestone-based; GoldBod to settle invoices within 30 days of milestone sign-off.
| Bank Guarantee | 10% performance bond/bank guarantee to be provided at contract signing.
| Source Code | Full source code, documentation and IP assigned to GoldBod upon final payment.
| Post-Handover Warranty | 12-month post-handover warranty commences at end of stabilisation phase (Month 18).

## 8. Deployment Costs
SECTION 8 — DEPLOYMENT COSTS (Pilot & National Rollout)
Deployment Activity / Item | Estimated Cost (USD) | Estimated Cost (GHS)
PILOT DEPLOYMENT — 3 MINE SITES (Months 5–6)
Pilot site survey & readiness assessment (3 sites) | 15000 | 195000
Site-specific hardware installation & configuration | 18000 | 234000
Blockchain node deployment at pilot sites | 8000 | 104000
Network & connectivity setup at pilot sites | 12000 | 156000
Pilot data migration & historical records import | 10000 | 130000
Pilot user onboarding & account provisioning | 6000 | 78000
On-site pilot training & orientation (3 sites × 3 days) | 12000 | 156000
Pilot monitoring, war room & daily standups | 9000 | 117000
Field feedback sessions & UX iteration | 7000 | 91000
Pilot performance report & go/no-go assessment | 5000 | 65000
Pilot closeout & lessons-learned documentation | 4000 | 52000
Sub-Total | 106000 | 1378000
PRE-NATIONAL DEPLOYMENT PREPARATION
National deployment planning & runbook development | 8000 | 104000
Infrastructure pre-provisioning (all 10 regions) | 22000 | 286000
Bulk hardware staging, testing & labelling | 9000 | 117000
National data migration & master data setup | 18000 | 234000
User account bulk provisioning (all actors) | 10000 | 130000
Stakeholder pre-briefing (10 regional offices) | 12000 | 156000
Pre-deployment penetration test & sign-off | 15000 | 195000
Sub-Total | 94000 | 1222000
NATIONAL GO-LIVE — 10 REGIONS (Month 6)
Regional equipment delivery & logistics (10 regions) | 28000 | 364000
On-site installation teams (10 teams × 3 technicians, 3 days) | 30000 | 390000
Network/connectivity activation across all sites | 15000 | 195000
Go-live war room (24/7 support — 2 weeks) | 22000 | 286000
National launch event & press conference | 15000 | 195000
Public awareness campaign (radio, TV, billboards) | 20000 | 260000
SMS broadcast to all registered miners/buyers | 3000 | 39000
Post go-live hotfix sprints (first 4 weeks) | 18000 | 234000
Regional helpdesk activation & staffing | 14000 | 182000
Go-live documentation & sign-off pack | 5000 | 65000
Sub-Total | 170000 | 2210000
CLOUD & INFRASTRUCTURE SCALE-UP AT GO-LIVE
Auto-scaling configuration & load testing at national volume | 8000 | 104000
CDN & caching optimisation for Ghana latency | 5000 | 65000
Disaster recovery drill at go-live scale | 6000 | 78000
Blockchain node replication & geo-distribution | 7000 | 91000
Monitoring dashboards configuration (real-time) | 4000 | 52000
Sub-Total | 30000 | 390000
TOTAL DEPLOYMENT COSTS | 400000 | 5200000

## 9. Training & Capacity
SECTION 9 — TRAINING & CAPACITY BUILDING COSTS
Training Activity | Unit Cost (USD) | Qty | Total USD | Total GHS
TRAINING PROGRAMME DESIGN & MATERIALS
Training Needs Assessment & Skills Gap Analysis | 12000 | 1 | 12000 | 156000
Curriculum Design (all 8 user roles) | 18000 | 1 | 18000 | 234000
User Manuals & Quick Reference Guides (all roles) | 10000 | 1 | 10000 | 130000
Video Tutorial Production (16 modules) | 2500 | 16 | 40000 | 520000
Interactive E-Learning Modules (LMS) | 3000 | 8 | 24000 | 312000
Poster & Visual Aid Design (local languages) | 5000 | 1 | 5000 | 65000
LMS Platform Setup & Content Upload | 8000 | 1 | 8000 | 104000
Training Material Translation (Twi, Hausa, Dagbani) | 6000 | 1 | 6000 | 78000
Sub-Total |  |  | 123000 | 1599000
GOLDBOD TECHNICAL STAFF TRAINING
Blockchain Technology & Node Management (5-day) | 8000 | 1 | 8000 | 104000
System Administration & DevOps (3-day) | 5000 | 1 | 5000 | 65000
Database Administration & Backup (2-day) | 3500 | 1 | 3500 | 45500
Security & Incident Response Training (2-day) | 4000 | 1 | 4000 | 52000
Analytics & BI Dashboard Training (2-day) | 3000 | 1 | 3000 | 39000
API Integration & Developer Training (3-day) | 4500 | 1 | 4500 | 58500
Sub-Total |  |  | 28000 | 364000
FIELD OFFICER TRAINING (10 REGIONS)
Train-the-Trainer Programme (20 regional trainers) | 8000 | 1 | 8000 | 104000
Field Officer Training — Region 1 (Greater Accra) | 3500 | 2 | 7000 | 91000
Field Officer Training — Region 2 (Ashanti) | 3500 | 2 | 7000 | 91000
Field Officer Training — Region 3 (Western) | 3500 | 2 | 7000 | 91000
Field Officer Training — Region 4 (Eastern) | 3500 | 2 | 7000 | 91000
Field Officer Training — Region 5 (Brong-Ahafo) | 3500 | 2 | 7000 | 91000
Field Officer Training — Regions 6–10 (Northern zones) | 4500 | 2 | 9000 | 117000
Field Training Logistics (venue, transport, per diem/region) | 1200 | 10 | 12000 | 156000
Sub-Total |  |  | 64000 | 832000
INDUSTRY ACTOR TRAINING
Tier 1 & 2 Licensed Buyer Training (30 sessions) | 2500 | 30 | 75000 | 975000
Kitchen / Aggregator Operator Training (20 sessions) | 2000 | 20 | 40000 | 520000
Transporter & Logistics Operator Training (15 sessions) | 1800 | 15 | 27000 | 351000
ASM / Small-Scale Miner Sensitisation (40 community sessions) | 1500 | 40 | 60000 | 780000
Large-Scale Mine Corporate User Training (10 companies) | 3000 | 10 | 30000 | 390000
Export / Trading Company Training (15 sessions) | 2500 | 15 | 37500 | 487500
Sub-Total |  |  | 269500 | 3503500
REFRESHER & STABILISATION TRAINING (Months 7–18)
Quarterly refresher workshops (all roles, 4 cycles) | 12000 | 1 | 12000 | 156000
On-demand coaching & remote support sessions | 8000 | 1 | 8000 | 104000
New feature release training (per quarterly release) | 4000 | 4 | 16000 | 208000
Helpdesk script & FAQ update training | 3000 | 1 | 3000 | 39000
Sub-Total |  |  | 39000 | 507000
CHANGE MANAGEMENT PROGRAMME
Stakeholder communication strategy & materials | 8000 | 1 | 8000 | 104000
Change champion identification & coaching | 6000 | 1 | 6000 | 78000
Resistance management & user adoption workshops | 5000 | 1 | 5000 | 65000
Adoption monitoring & reporting (18 months) | 6000 | 1 | 6000 | 78000
Sub-Total |  |  | 25000 | 325000
TOTAL TRAINING & CAPACITY BUILDING |  |  | 548500 | 7130500

## 10. Integration Costs
SECTION 10 — INTEGRATION & INTEROPERABILITY COSTS
Integration / API Activity | Unit Cost (USD) | Qty | Total USD | Total GHS
GOVERNMENT AGENCY INTEGRATIONS
Minerals Commission — Licensing & Cadastre API (dev+test) | 45000 | 1 | 45000 | 585000
Ghana Revenue Authority — Customs Export Verification API | 40000 | 1 | 40000 | 520000
Bank of Ghana — Payment & FX Reporting API | 45000 | 1 | 45000 | 585000
Financial Intelligence Centre — STR/SAR e-Filing | 38000 | 1 | 38000 | 494000
Environmental Protection Authority — Permit API | 32000 | 1 | 32000 | 416000
Water Resources Commission — Compliance API | 28000 | 1 | 28000 | 364000
Ghana Card / NIA — Identity Verification API | 20000 | 1 | 20000 | 260000
Government Agency Integration Testing & Validation | 25000 | 1 | 25000 | 325000
Ongoing Integration Maintenance (12 months) | 18000 | 1 | 18000 | 234000
Sub-Total |  |  | 291000 | 3783000
PAYMENT & FINANCIAL INTEGRATIONS
MTN Mobile Money API Integration & Certification | 12000 | 1 | 12000 | 156000
Vodafone Cash API Integration | 10000 | 1 | 10000 | 130000
AirtelTigo Money API Integration | 8000 | 1 | 8000 | 104000
Bank Payment Gateway Integration (GhIPSS) | 15000 | 1 | 15000 | 195000
Transaction Fee Provision (est. avg 0.5% — 18 months) | 18000 | 1 | 18000 | 234000
Sub-Total |  |  | 63000 | 819000
COMPLIANCE & SCREENING INTEGRATIONS
AML/CFT Sanctions Screening API (OFAC/EU/UN lists) | 24000 | 1 | 24000 | 312000
PEP & Adverse Media Screening Service | 18000 | 1 | 18000 | 234000
Beneficial Ownership Verification Service | 12000 | 1 | 12000 | 156000
Annual API subscription renewal (stabilisation phase) | 15000 | 1 | 15000 | 195000
Sub-Total |  |  | 69000 | 897000
COMMUNICATION & NOTIFICATION INTEGRATIONS
Bulk SMS Gateway — MTN/Vodafone Ghana (setup + 18 mths) | 9600 | 1 | 9600 | 124800
Email Delivery Service (SendGrid/AWS SES — 18 mths) | 3600 | 1 | 3600 | 46800
WhatsApp Business API (optional notifications) | 6000 | 1 | 6000 | 78000
Push Notification Service (FCM/APNs) | 2400 | 1 | 2400 | 31200
Sub-Total |  |  | 21600 | 280800
GEOLOCATION & MAPPING INTEGRATIONS
Google Maps Platform API (Places, Geocoding, Routes) | 9000 | 1 | 9000 | 117000
GPS Tracker Fleet Management Integration | 5000 | 1 | 5000 | 65000
Geofencing Rules Engine (mining zone boundaries) | 8000 | 1 | 8000 | 104000
Sub-Total |  |  | 22000 | 286000
API MANAGEMENT & DEVELOPER INFRASTRUCTURE
API Gateway Setup & Configuration (Kong/AWS API GW) | 12000 | 1 | 12000 | 156000
API Documentation Portal (Swagger/Redoc) | 5000 | 1 | 5000 | 65000
API Versioning & Lifecycle Management Tools | 4000 | 1 | 4000 | 52000
Developer Sandbox Environment (18 months) | 6000 | 1 | 6000 | 78000
API Security — Rate Limiting, OAuth2, mTLS | 8000 | 1 | 8000 | 104000
Sub-Total |  |  | 35000 | 455000
DATA MIGRATION & LEGACY INTEGRATION
Existing GoldBod Records — ETL Extraction & Cleansing | 18000 | 1 | 18000 | 234000
Historical Transaction Data Migration & Validation | 15000 | 1 | 15000 | 195000
Parallel Run Support (legacy + new system overlap) | 10000 | 1 | 10000 | 130000
Data Quality Assessment & Remediation | 8000 | 1 | 8000 | 104000
Sub-Total |  |  | 51000 | 663000
TOTAL INTEGRATION & INTEROPERABILITY COSTS |  |  | 552600 | 7183800

## 11. Testing & QA
SECTION 11 — TESTING & QUALITY ASSURANCE COSTS
Testing Activity | Unit Cost (USD) | Qty | Total USD | Total GHS
TEST INFRASTRUCTURE & ENVIRONMENTS
Test Environment Hosting — UAT + Staging (6 months) | 5000 | 6 | 30000 | 390000
Test Data Generation & Masking Tools | 6000 | 1 | 6000 | 78000
Test Automation Framework Setup (Selenium/Appium/Cypress) | 18000 | 1 | 18000 | 234000
Performance Testing Tool — JMeter/Gatling Setup | 8000 | 1 | 8000 | 104000
Mobile Device Testing Lab (Android/iOS physical devices) | 12000 | 1 | 12000 | 156000
BrowserStack Cloud Testing Subscription (6 months) | 3000 | 6 | 18000 | 234000
Defect Tracking Tool License — Jira (18 months) | 2000 | 1 | 2000 | 26000
Sub-Total |  |  | 94000 | 1222000
FUNCTIONAL TESTING
Unit Testing (developer-led, covered in dev cost) | 0 | 1 | 0 | 0
Integration Testing — all 6 agency APIs | 15000 | 1 | 15000 | 195000
System Testing — end-to-end functional scenarios | 12000 | 1 | 12000 | 156000
Regression Testing (per sprint — 12 sprints) | 2000 | 12 | 24000 | 312000
User Acceptance Testing — GoldBod staff (facilitated) | 15000 | 1 | 15000 | 195000
UAT — Industry actors (buyers, miners, transporters) | 10000 | 1 | 10000 | 130000
Sub-Total |  |  | 76000 | 988000
NON-FUNCTIONAL TESTING
Performance & Load Testing (target: 10,000 concurrent users) | 18000 | 1 | 18000 | 234000
Stress Testing & Capacity Planning | 8000 | 1 | 8000 | 104000
Scalability Testing — national transaction volumes | 6000 | 1 | 6000 | 78000
Offline Mode & Network Resilience Testing | 5000 | 1 | 5000 | 65000
Disaster Recovery Failover Testing | 8000 | 1 | 8000 | 104000
Blockchain Consensus & Fault Tolerance Testing | 12000 | 1 | 12000 | 156000
Sub-Total |  |  | 57000 | 741000
SECURITY TESTING
External Penetration Testing — Web & API (OWASP top 10) | 35000 | 1 | 35000 | 455000
Mobile App Security Testing (Android & iOS) | 15000 | 1 | 15000 | 195000
Blockchain Smart Contract Security Audit | 25000 | 1 | 25000 | 325000
Vulnerability Assessment & Remediation Review | 12000 | 1 | 12000 | 156000
Data Privacy & GDPR/Act 843 Compliance Scan | 8000 | 1 | 8000 | 104000
Source Code Review (external firm) | 18000 | 1 | 18000 | 234000
Sub-Total |  |  | 113000 | 1469000
COMPLIANCE & STANDARDS TESTING
LBMA Responsible Gold Guidance Compliance Assessment | 20000 | 1 | 20000 | 260000
OECD Due Diligence Guidance Alignment Review | 15000 | 1 | 15000 | 195000
ISO 27001 Gap Analysis & Internal Audit | 18000 | 1 | 18000 | 234000
AML/CFT Controls Testing (FATF Recommendations) | 12000 | 1 | 12000 | 156000
Accessibility Testing (WCAG 2.1 — government portal) | 5000 | 1 | 5000 | 65000
Sub-Total |  |  | 70000 | 910000
TEST DOCUMENTATION & REPORTING
Test Strategy & Master Test Plan | 6000 | 1 | 6000 | 78000
Test Cases & Test Scripts (all modules) | 8000 | 1 | 8000 | 104000
Traceability Matrix (requirements ↔ test cases) | 4000 | 1 | 4000 | 52000
Test Completion Reports & Sign-off Packs | 3000 | 1 | 3000 | 39000
Defect Reports & Root Cause Analysis Documentation | 3000 | 1 | 3000 | 39000
Sub-Total |  |  | 24000 | 312000
TOTAL TESTING & QA COSTS |  |  | 434000 | 5642000

## 12. PMO & Governance
SECTION 12 — PROJECT MANAGEMENT & GOVERNANCE COSTS
PMO Activity / Item | Unit Cost (USD) | Qty / Mths | Total USD | Total GHS
PMO SETUP & TOOLS
PMO Office Setup & Fit-Out (18 months rental incl.) | 3000 | 18 | 54000 | 702000
Project Management Software (MS Project / Smartsheet) | 2500 | 1 | 2500 | 32500
Document Management System (SharePoint / Confluence) | 2000 | 1 | 2000 | 26000
Time Tracking & Resource Management Tool | 1200 | 1 | 1200 | 15600
Risk Management Tool License | 1500 | 1 | 1500 | 19500
Gantt Scheduling & Baseline Management | 1000 | 1 | 1000 | 13000
Video Conferencing & Collaboration (Zoom/Teams — 18 mths) | 3600 | 1 | 3600 | 46800
Sub-Total |  |  | 65800 | 855400
GOVERNANCE & REPORTING
Monthly Steering Committee Meetings (venue + facilitation) | 1200 | 18 | 21600 | 280800
Technical Review Board Meetings (bi-monthly, 9 meetings) | 800 | 9 | 7200 | 93600
Monthly Progress Reports Preparation | 1500 | 18 | 27000 | 351000
Quarterly Financial Reports | 2000 | 6 | 12000 | 156000
Risk & Issue Log Maintenance | 500 | 18 | 9000 | 117000
Change Request Management & Documentation | 1000 | 18 | 18000 | 234000
Quality Assurance Reviews (monthly) | 1000 | 18 | 18000 | 234000
Compliance Status Reports (bi-monthly) | 800 | 9 | 7200 | 93600
Sub-Total |  |  | 120000 | 1560000
STAKEHOLDER ENGAGEMENT & EVENTS
Project Launch Kickoff Event | 8000 | 1 | 8000 | 104000
National Go-Live Ceremony | 15000 | 1 | 15000 | 195000
Regional Stakeholder Engagement Workshops (10 regions) | 3000 | 10 | 30000 | 390000
Ministerial / Board Briefing Packs (quarterly) | 1500 | 6 | 9000 | 117000
Public Relations & Media Engagement Programme | 10000 | 1 | 10000 | 130000
Communication Materials (brochures, flyers, rollup banners) | 6000 | 1 | 6000 | 78000
Project Close-Out Workshop & Handover Ceremony | 8000 | 1 | 8000 | 104000
Sub-Total |  |  | 86000 | 1118000
TRAVEL & LOGISTICS
International Airfare — Expert Missions to Ghana (4 visits) | 5000 | 4 | 20000 | 260000
Accommodation & Per Diem — International Experts (4 stays) | 3500 | 4 | 14000 | 182000
Domestic Air Travel — Regional Oversight Visits | 1500 | 10 | 15000 | 195000
Ground Transport — Project Team (18 months) | 1000 | 18 | 18000 | 234000
Equipment Transportation & Delivery Logistics | 8000 | 1 | 8000 | 104000
Emergency / Urgent Travel Reserve | 5000 | 1 | 5000 | 65000
Sub-Total |  |  | 80000 | 1040000
ADMINISTRATIVE & OFFICE COSTS
Office Utilities & Internet (18 months) | 1000 | 18 | 18000 | 234000
Printing, Stationery & Office Supplies | 500 | 18 | 9000 | 117000
Courier & Document Delivery | 300 | 18 | 5400 | 70200
Bank Charges & Transfer Fees (18 months) | 400 | 18 | 7200 | 93600
Contingency Admin Reserve | 5000 | 1 | 5000 | 65000
Sub-Total |  |  | 44600 | 579800
TOTAL PMO & GOVERNANCE COSTS |  |  | 396400 | 5153200

## 13. Compliance & Regulatory
SECTION 13 — COMPLIANCE & REGULATORY COSTS
Compliance Activity | Estimated Cost (USD) | Estimated Cost (GHS)
GHANA LEGAL & REGULATORY COMPLIANCE
Data Protection Act 843 — DPIA & Privacy Impact Assessment | 12000 | 156000
Privacy Policy & Data Processing Agreements (legal drafting) | 8000 | 104000
Data Protection Commission Registration & Filing | 2000 | 26000
AML Act 1044 — AML/CFT Policy & Controls Framework | 10000 | 130000
Ghana Gold Board Act 1140 — Regulatory Alignment Review | 8000 | 104000
Public Procurement Act Compliance — Documentation & Filings | 5000 | 65000
Withholding Tax Provision on Foreign Service Payments | 20000 | 260000
VAT on Applicable Local Costs (15% provision) | 15000 | 195000
SSNIT, PAYE & Pension Compliance Administration (18 months) | 12000 | 156000
Tax Clearance Certificate & GRA Filings | 3000 | 39000
PPA Supplier Registration & Bidding Documentation | 4000 | 52000
Sub-Total | 99000 | 1287000
INTERNATIONAL STANDARDS COMPLIANCE
OECD Due Diligence Guidance — Framework Implementation | 15000 | 195000
LBMA Responsible Gold Guidance — Compliance Programme | 18000 | 234000
FATF Recommendations Alignment — Controls Mapping | 10000 | 130000
RMI (Responsible Minerals Initiative) Compliance Assessment | 12000 | 156000
ICGLR Certification Programme Alignment | 8000 | 104000
Sub-Total | 63000 | 819000
INFORMATION SECURITY & CERTIFICATIONS
ISO 27001 Gap Analysis & Readiness Assessment | 18000 | 234000
ISO 27001 Certification Audit (external certification body) | 25000 | 325000
SOC 2 Type II Readiness & Audit | 30000 | 390000
Blockchain Technology Certification (specialist body) | 8000 | 104000
Annual Security Compliance Review (18 months) | 10000 | 130000
Sub-Total | 91000 | 1183000
INTELLECTUAL PROPERTY & CONTRACTS
IP Assignment Agreement — Full Source Code & Documentation | 8000 | 104000
Open Source Licence Compliance Review | 4000 | 52000
Third-Party Vendor Contract Review (legal) | 6000 | 78000
Source Code Escrow Agreement Setup & Annual Fee | 5000 | 65000
Patent / Trademark Searches (if applicable) | 3000 | 39000
Sub-Total | 26000 | 338000
INSURANCE
Professional Indemnity Insurance (18 months) | 18000 | 234000
Cyber Liability Insurance (18 months) | 14000 | 182000
Project Insurance & Contractor All-Risk (18 months) | 10000 | 130000
Hardware & Equipment Insurance (18 months) | 8000 | 104000
Employer's Liability Insurance (Ghana staff, 18 months) | 6000 | 78000
Sub-Total | 56000 | 728000
AUDIT & EXTERNAL ASSURANCE
Annual Financial Audit (Year 1 project accounts) | 12000 | 156000
External IT Audit — System Controls & Access Review | 10000 | 130000
AML/CFT Controls Effectiveness Review (external firm) | 12000 | 156000
Data Protection Audit (post go-live, Month 9) | 8000 | 104000
Project Close-Out Audit & Asset Verification | 6000 | 78000
Sub-Total | 48000 | 624000
TOTAL COMPLIANCE & REGULATORY COSTS | 383000 | 4979000

## 14. Documentation
SECTION 14 — DOCUMENTATION & DELIVERABLES COSTS
Document / Deliverable | Estimated Cost (USD) | Estimated Cost (GHS)
TECHNICAL DOCUMENTATION
System Architecture & Design Document (SDD) | 8000 | 104000
Blockchain Network Architecture Specification | 5000 | 65000
API Reference Documentation & Swagger/OpenAPI Specs | 5000 | 65000
Database Schema & Data Dictionary | 4000 | 52000
Security Architecture & Threat Model Document | 5000 | 65000
Infrastructure-as-Code Documentation (Terraform/Ansible) | 3000 | 39000
DevOps & CI/CD Pipeline Documentation | 3000 | 39000
Disaster Recovery & Business Continuity Plan (BCP) | 6000 | 78000
Source Code Repository Documentation & README files | 3000 | 39000
Sub-Total | 42000 | 546000
USER-FACING DOCUMENTATION
System Administrator Manual | 6000 | 78000
Field Officer User Manual (Android App) | 5000 | 65000
Web Portal User Guide (all roles) | 5000 | 65000
Miner / ASM Simplified Usage Guide (pictorial, local lang.) | 4000 | 52000
Tier 1/2 Buyer User Manual | 4000 | 52000
Aggregator & Transporter User Guide | 3000 | 39000
Help Desk / L1 Support Runbook | 4000 | 52000
FAQ Document & Troubleshooting Guide | 3000 | 39000
Sub-Total | 34000 | 442000
COMPLIANCE & GOVERNANCE DOCUMENTS
Data Protection & Privacy Policy | 4000 | 52000
AML/CFT Compliance Manual & Procedures | 5000 | 65000
OECD/LBMA Compliance Framework Documentation | 6000 | 78000
Change Management & Escalation Procedures | 3000 | 39000
Incident Response & Security Breach Plan | 4000 | 52000
System Audit Trail & Access Log Specification | 3000 | 39000
SLA Definition & Performance KPI Framework | 4000 | 52000
Sub-Total | 29000 | 377000
PROJECT MANAGEMENT DOCUMENTS
Project Initiation Document (PID) & Project Charter | 3000 | 39000
Project Schedule (Gantt) & Work Breakdown Structure | 2000 | 26000
18 Monthly Progress Reports | 1500 | 19500
Risk Register & Issue Log (maintained 18 months) | 2000 | 26000
Change Request Log & Change Management Register | 1500 | 19500
Monthly Financial Reports & Budget Variance Reports | 2000 | 26000
Lessons Learned Register (ongoing) | 1500 | 19500
Project Closure Report | 4000 | 52000
Sub-Total | 17500 | 227500
HANDOVER & SUSTAINABILITY DOCUMENTS
Knowledge Transfer Plan & Schedule | 4000 | 52000
System Handover Pack (all documentation compiled) | 6000 | 78000
Source Code Handover & Repository Transfer Documentation | 5000 | 65000
Staff Capability Assessment & Training Completion Certificates | 3000 | 39000
Post-Handover Warranty Terms & Support Agreement | 3000 | 39000
Long-Term Sustainability & Operational Plan | 5000 | 65000
Technology Refresh Roadmap (3-year horizon) | 4000 | 52000
Sub-Total | 30000 | 390000
TRAINING MATERIALS (as deliverables)
LMS with all e-learning modules (handed over to GoldBod) | 8000 | 104000
Printed training materials (1,000 sets — all roles) | 4000 | 52000
Video tutorial library (16 HD videos, hosted) | 5000 | 65000
Assessment & certification exam materials | 2000 | 26000
Sub-Total | 19000 | 247000
TOTAL DOCUMENTATION & DELIVERABLES COSTS | 171500 | 2229500

## 15. Contingency Budget
SECTION 15 — CONTINGENCY BUDGET
Contingency is provisioned at 10% of direct costs per category. Release requires written PMO approval. Unspent contingency is returned to GoldBod.
| Cost Category | Direct Cost (USD) | Contingency Rate | Contingency (USD) | Contingency (GHS)
| 1 | Personnel & HR Costs | 3250000 | 8% | 260000 | 3380000
| 2 | Software Development | 1980000 | 12% | 237600 | 3088800
| 3 | Blockchain Infrastructure | 820000 | 12% | 98400 | 1279200
| 4 | Cloud & Hosting (18 months) | 540000 | 8% | 43200 | 561600
| 5 | Software Licenses & Tools | 310000 | 5% | 15500 | 201500
| 6 | Hardware & Field Equipment | 680000 | 10% | 68000 | 884000
| 7 | Deployment Costs | 400000 | 10% | 40000 | 520000
| 8 | Systems Integration (6 agencies + APIs) | 640000 | 15% | 96000 | 1248000
| 9 | Testing & Quality Assurance | 290000 | 10% | 29000 | 377000
| 10 | Training & Capacity Building | 420000 | 10% | 42000 | 546000
| 11 | Compliance & Regulatory | 180000 | 8% | 14400 | 187200
| 12 | Project Management & PMO | 380000 | 8% | 30400 | 395200
| 13 | Documentation & Deliverables | 95000 | 5% | 4750 | 61750
| 14 | Additional Risk Reserve (currency/tax) | 250000 | 100% | 250000 | 3250000
| TOTAL CONTINGENCY PROVISION |  |  |  | 1229250 | 15980250
CONTINGENCY POLICY:
1. Contingency funds are NOT automatic — each draw requires a formal Contingency Release Request (CRR) approved by GoldBod PMO Director.
2. Draws ≤ USD 10,000 may be approved by the Project Manager. Draws > USD 10,000 require Steering Committee approval.
3. Category rates reflect complexity: Integration (15%) and Software Dev (12%) carry higher rates due to scope uncertainty.
4. Currency/Tax Reserve (Line 14) covers GHS exchange rate movements >5% or unbudgeted tax policy changes.
5. Any unspent contingency at project close is returned to GoldBod and not retained by the implementing vendor.
6. A contingency utilisation report is included in each monthly progress report.

## 16. Financial Impact & ROI
GOLDBOD — FINANCIAL IMPACT ANALYSIS: TAS IMPLEMENTATION BUSINESS CASE
This sheet models GoldBod's current baseline revenues, estimated revenue leakage, and the projected financial gains from the TAS. All figures are estimates based on Ghana Gold Board Act 2025, Bank of Ghana data, and regional ASM sector benchmarks.
PART A — GOLDBOD CURRENT FINANCIAL BASELINE (Pre-TAS, Annual Estimates)
| Revenue / Income Stream | Annual Volume | Gold Price Basis (USD/oz) | Annual Revenue (USD) | Annual Revenue (GHS)
| Gold Purchased from ASM Sector (est. 30 tonnes/yr) | 30 tonnes | 2150 | 2073675000 | 26957775000
| Export Levy Revenue (est. 3% on export value) | Levy | 2150 | 62210250 | 808733250
| Licensing & Permit Fees (all categories) | Fixed |  | 8500000 | 110500000
| Assay & Certification Fees | Per assay |  | 2200000 | 28600000
| Administrative / Service Fees | Various |  | 1800000 | 23400000
| Fines & Penalties (enforcement actions) | Variable |  | 900000 | 11700000
| ESTIMATED TOTAL ANNUAL BASELINE REVENUE |  |  | 2149285250 | 27940708250
PART B — ESTIMATED ANNUAL REVENUE LEAKAGE (Current, Pre-TAS)
| Leakage Category | Mechanism / Description | Leakage Rate | Leakage USD/yr | Leakage GHS/yr
| Gold Smuggling & Illicit Export | Unregistered gold bypassing GoldBod, exported via neighbouring countries | 25% | 518418750 | 6739443750
| Under-Declaration of Weight / Grade | Miners & buyers under-report quantity and purity at assay points | 12% | 248841000 | 3234933000
| Export Levy Avoidance | Exporters misclassify gold as semi-processed or use false invoices | 30% | 18663075 | 242619975
| Royalty Under-Payment (ASM sector) | ASM operators under-declare production volumes to GRA | 20% | 20736750 | 269577750
| Ghost Licensing / Duplicate Registrations | Multiple registrations for same operation; expired licences still trading | 5% | 425000 | 5525000
| Fictitious KYC / Beneficial Ownership Concealment | Shell companies hide true owners; AML controls bypassed | 10% | 900000 | 11700000
| Corrupt Assay Certification | Bribed assay staff certify incorrect weights/grades | 8% | 165894000 | 2156622000
| Untracked Artisanal Mining Sites | ~35% of ASM sites unregistered; zero revenue captured | 35% | 21773587 | 283056631
| ESTIMATED TOTAL ANNUAL REVENUE LEAKAGE |  |  | 995652162 | 12943478106
PART C — TAS PROJECTED IMPACT: ANNUAL GAINS (Post-Implementation, Yr 2 Onwards)
| Benefit / Gain Category | Recovery / Impact Mechanism | Recovery Rate (TAS) | Annual Gain (USD) | Annual Gain (GHS)
| Illicit Export Reduction | Blockchain chain-of-custody makes undocumented gold unsaleable internationally | 60% | 311051250 | 4043666250
| Weight/Grade Under-Declaration Prevention | Digital scales + immutable ledger records eliminate manual tampering | 80% | 199072800 | 2587946400
| Export Levy Capture Improvement | Automated GRA API cross-matching eliminates false invoices | 70% | 13064152 | 169833976
| Royalty Revenue Recovery | GPS-tagged production sites + digital weighing closes ASM under-reporting gap | 65% | 13478887 | 175225531
| New Licences & Registrations (formalisation of unregistered ASM) | TAS incentivises formal registration for market access; 2,000 new licences est. | 100% | 6000000 | 78000000
| Assay Fee Revenue Increase (volume uplift from formalisation) | More formal actors → more assay events → more fee income | 100% | 3500000 | 45500000
| AML/CFT Fines & Penalty Revenue | FIC integration enables automated STR detection & enforcement actions | 100% | 2200000 | 28600000
| Reduced Operational Costs — Manual Processing Elimination | Digital workflows replace paper-based processes; headcount redeployed | 100% | 4800000 | 62400000
| Premium Pricing — LBMA/OECD Responsible Sourcing Certificate | TAS-certified Ghanaian gold commands 1-3% price premium on international markets | 100% | 31105125 | 404366625
| Ghana Card KYC Cost Savings (replacing manual ID verification) | Automated digital ID reduces compliance officer workload | 100% | 1200000 | 15600000
| Reduced Gold Sector Corruption Investigations | Immutable audit trail reduces legal/investigation costs to government | 100% | 2500000 | 32500000
| Improved Investor Confidence (FDI premium — long-term benefit est.) | Transparent, certified supply chain attracts responsible mining investment | 100% | 10000000 | 130000000
| TOTAL ESTIMATED ANNUAL GAIN (from Year 2) |  |  | 597972214 | 7773638782
PART D — RETURN ON INVESTMENT (ROI) SUMMARY
| Total TAS Project Investment (18 months) | USD |  | 11355000 | 147615000
| Estimated Annual Gain from Year 2 | USD |  | 597972214
| Payback Period | Months |  | ~14 months post go-live
| 5-Year Cumulative Net Gain (Yrs 2–6) | USD |  | 2978506070
| 10-Year Cumulative Net Gain (Yrs 2–11) | USD |  | 5968367140
| ROI at Year 3 (net gain / investment) | % |  | 10432%
| ROI at Year 5 | % |  | 20965%
| Benefit-to-Cost Ratio (Year 5) | x |  | 210.6463
DISCLAIMER: All baseline revenue, leakage and gain estimates are derived from public data (Bank of Ghana, Minerals Commission, PMMC reports), IMF Ghana Article IV consultations, and sector benchmarks. Actual outcomes will vary based on compliance rates, gold price movements, and implementation quality. These figures are for decision-support purposes and are conservative estimates.